ATTACHMENT A

EDITORIAL SERVICES CONTRACT

PERFORMANCE WORK STATEMENT

I. BACKGROUND	1

II. INTRODUCTION	1

III. SCOPE OF WORK	3

IV. PERFORMANCE REQUIREMENTS SUMMARY	9

PHASE A: PLANNING AND PREPARATION	9

IV.A.1: Defining Project Procedures; Producing a Procedures Manual and a Quality Control Plan	9

IV.A.2: Participating In, and Providing, Training	10

IV.A.3: Installing and Testing Equipment to Ensure Successful Contract Operation	11

IV.A.4: Meeting Security Requirements	15

PHASE B: PRODUCTION	22

IV.B.1: Answering Control Correspondence	22
IV.B.2: Answering Non-Control Correspondence (Paper and Electronic Mail [E-Mail])	29

IV.B.3: Accessing the Contractor’s Data Base(s) and E-Mail History	36

IV.B.4: Supplying Staff with Dictionaries and Writing/Style Guides	37

IV.B.5: Providing Courier Service	38

IV.B.6: Preparing Control and Non-Control Correspondence Reports and Other Reports	38

IV.B.7: Updating Standard Paragraphs, Form Letters, and Fact Sheets	39

IV.B.8: Preparing Correspondence Responses in Languages  Other Than English	41

IV.B.9: Translating into Spanish, and Preparing Layout for, Certain ED Publications	41

IV.B.10: Requesting Financial Aid Transcripts	42

IV.B.11: Updating the OSFAP Regulations Compilation	42

IV.B.12: Mailing Materials	43

IV.B.13 Updating the Procedures Manual and the Quality Control Plan	43

IV.B.14: Updating the Security Plan	43

IV.B.15: Updating and Implementing the Disaster Recovery

Plan	44

IV.B.16: Updating Network Drawings	44

IV.B.17: Maintaining Access to Different Data Bases	44

IV.B.18: Maintaining Systems Security Safeguards	45

IV.B.19: Producing Labels	46

IV.B.20: Photocopying	46

IV.B.21: Shredding/Erasing Materials	46

IV.B.22: Participating In, and Providing, Training	47

IV.B.23: Participating in Conference Calls	48

IV.B.24: Assisting During Transition Period	48

# I. BACKGROUND

For more than 20 years, the U.S. Department of Education (ED) has used contract services to prepare prompt and thorough responses to correspondence from the general public concerning financial assistance programs for postsecondary students. The general public either contacts ED directly or contacts the White House and members of Congress, who forward the correspondence to ED. In the past, ED’s Public Inquiry Contract (PIC) has prepared these responses in addition to performing other tasks, such as answering telephone inquiries received through the toll-free telephone line at ED’s Federal Student Aid Information Center (FSAIC). ED has decided to separate part of the PIC’s functions: The PIC will continue to answer correspondence concerning defaulted student loans ED holds, handle telephone lines at the FSAIC, and mail bulk orders of ED informational materials, among other functions. The Editorial Services Contract (ESC) will prepare the remainder of correspondence ED receives and will perform other editorial tasks, as specified below.

# II. INTRODUCTION

ED, through its Office of Student Financial Assistance Programs (OSFAP) office, requires contract services to

• prepare detailed and accurate responses to a very high volume of correspondence about the postsecondary student aid programs that the Higher Education Act of 1965, as amended, has established (Title IV programs).

• provide twice daily courier service to pick up and deliver correspondence and other materials ED will specify.

• prepare various reports, including weekly and monthly reports concerning control and non-control correspondence.

• update ED’s set of approximately 1,200 standard paragraphs, nearly 300 form letters, and approximately 10-12 fact sheets to ensure they provide current information about ED’s programs.

• translate correspondence into, and prepare responses in, languages other than English.

• translate into Spanish, and prepare in final form (using desktop publishing), federal student aid materials.

• provide information on financial aid transcripts to schools having difficulty obtaining these documents from other schools.

• update annually the OSFAP regulations compilation.

• provide miscellaneous ancillary services such as mailing single copies of ED informational materials, producing labels, and photocopying.

ED will use task orders for additional services ED might require over the life of the contract. The Contracting Officer will issue task orders upon the program office’s request. Unless otherwise noted, the contractor shall have 10 working days to prepare a proposal after receiving a Statement of Work for a proposed task order.

Task orders might involve

(1)	tracking control correspondence by computer, which would involve keeping electronic records of this correspondence (date received, name of inquirer, status of correspondence, completion dates, etc.)

(2)		electronically transmitting to, and receiving from, ED all incoming    correspondence.

(3) mailing correspondence (stuffing envelopes, etc.)

(4) preparing additional reports similar to those required under IV.B.6. For example, ED might require the contractor to record the amount of correspondence received resulting from a press release or a news item. ED might require the contractor to develop surveys and statistical information and provide reports based on the survey and statistical information findings. The contractor would have to collect, analyze, and assimilate data in preparing these reports. ED also might suggest categories for data collection and require the contractor to use charts and graphs to illustrate and enhance the reports.

(5) translating additional ED publications and materials into Spanish (similar to those required under IV.B.9).

(6) creating electronic versions of ED documents in formats for access through the Internet including, but not limited to, Hyper-Text Markup Language (HTML).

(7) converting Encapsulated Postscript (EPS) graphics files into Graphics Interchange Format (GIF) files and scanning images and converting them to GIF files.

(8) preparing publications and providing desktop publishing services. For example, ED might require the contractor to edit existing documents and to prepare documents in final form from existing drafts. ED might require the contractor to create new documents, such as general and technical publications or brochures for the public. To prepare these documents, the contractor might have to do research and write, edit, proofread, create graphics, and prepare final layout using desktop publishing. ED would expect the contractor to furnish these documents on disk and in hard copy. The disk(s) would have to contain a copy of the document in a Portable Document Format (PDF) file. ED most likely will require documents furnished in Macintosh versions of software that ED will specify at the time ED requires the contractor to prepare the publication(s). Text and layout programs ED currently uses include, but are not limited to, Microsoft Word, PageMaker, DeltaGraph, FreeHand, Photoshop, and Illustrator. ED also might require the contractor to furnish documents in IBM-compatible format.

ED also will issue Work Orders for discrete activities costing $10,000 or less. These Work Orders, which would relate to the task orders listed above, do not require the Contracting Officer’s approval. Upon receipt of a Work Order Request from the COTR, the contractor shall submit to the COTR the completed contractor section of the Work Order Request and shall propose a fixed price within five working days from the date the contractor receives the Work Order Request.

# III. SCOPE OF WORK

The work performed under this contract is expected to be conducted in two phases: Phase A, Planning and Preparation, and Phase B, Production. Phase A begins on the date ED awards the contract. ED will exercise Phase B as an option, based on whether the contractor demonstrates it can perform successfully all aspects of Phase A and be completely ready for startup by the end of Phase A. If ED exercises Phase B, that phase will begin approximately three months after the start of Phase A. This contract will consist of a Base Period and four Option Years.

The contractor shall be fully and successfully operational by the beginning of Phase B and shall, therefore, complete by the end of Phase A all preparatory activity: installing and testing equipment and internal software, hiring and/or training critical staff, developing and testing procedures, and meeting security requirements.

A. Supplemental Information

1. Correspondence

i. Control Correspondence

Control correspondence consists of inquiries that come directly from the general public or inquiries the White House and members of Congress refer to ED. ED currently tracks the progress of this correspondence by attaching a correspondence tracking sheet to each control letter; the sheet indicates, among other information, who wrote the letter, which ED office is responsible for answering the letter, and when the response is due in ED’s Executive Secretariat office. Regardless of that due date, however, the contractor must deliver completed responses to TPID within three working days after the contractor receives the correspondence. If the response requires the contractor to do casework (see section iv below), the contractor generally must deliver completed responses to ED within six working days after the contractor receives the correspondence.

The contractor will prepare responses by using ED’s set of approximately 1,200 standard paragraphs, available on disk; enclosing relevant ED publications and other materials, when appropriate; and/or using custom writing the contractor must prepare according to ED-established style guidelines (see IV.B.1.j).

ii. Non-Control Correspondence

Non-control correspondence consists of public inquiries (including electronic mail [e-mail]) that neither the White House nor members of Congress have referred. In general, preparing non-control responses requires less work than preparing control responses because the issues usually are simpler and more straightforward, although the contractor occasionally will have to do casework (see section iv below). ED does not officially track non-control correspondence but will sample the responses. The contractor must complete and send out responses within two working days after the contractor receives the incoming correspondence. If the response requires casework (see section iv below), the contractor generally must complete and send out responses within five working days after the contractor receives the correspondence.

For non-control correspondence, the contractor will prepare responses using ED’s set of approximately 300 form letters (available on disk). To answer the correspondence completely, however, the contractor will, in many cases, have to modify the form letters with custom writing and/or with standard paragraphs the contractor must add. When appropriate, the contractor also must, for paper responses, enclose relevant ED publications and other materials; for e-mail responses, the contractor must inform inquirers how to obtain those materials.

iii. Correspondence Volume

Correspondence volume is very high. Section J makes available a monthly breakdown of 1995, 1996, and 1997 correspondence volumes for control and non-control mail. Responding adequately requires the contractor to answer a voluminous amount of correspondence rapidly without sacrificing accuracy and clarity.

iv. Nature of Correspondence

Some student financial aid correspondence is fairly straightforward: For example, an inquirer might ask what federal student aid programs are available. (In such cases, often standard paragraphs are sufficient responses for control mail. For non-control mail, often form letter responses are sufficient.) Preparing responses for other correspondence requires a broader understanding of program issues: The inquirer might need an explanation of ED’s need analysis formula, for example, or might not understand the school’s role—and ED’s guidelines—in developing satisfactory academic progress standards, prorating an award, or calculating a refund policy for a student who withdraws.

A substantial amount of correspondence requires casework; this type of correspondence, which will usually (but not always) be control correspondence, has increased significantly over recent years. Casework requires the contractor to contact (usually by telephone) postsecondary schools, lenders, guarantee agencies, and servicing organizations, for example, to develop the information needed to respond. Casework responses require extensive research. For instance, a large amount of correspondence comes from federal student loan borrowers who have defaulted on their loans. Borrowers might disagree about the amount they owe or the number of payments they must make. Borrowers might complain about collection tactics agencies use or the fact that their U.S. tax refunds are being withheld to pay for the outstanding loan. The contractor must contact all appropriate entities involved with the loan, incorporating the findings into the response. The response generally must contain information including, but not limited to, how many loans the borrower has; when those loans entered repayment; how many payments were received and when they were received; and when the loans went into default. If a borrower complains he or she was not contacted about making loan payments, the contractor must include how many times the lender, servicing agency, and/or guarantee agency contacted, or attempted to contact, the borrower. Because these are not all-inclusive examples of what the contractor must cover in a response, ED requires the contractor to respond completely, accurately, and clearly to all issues in each piece of correspondence. Given the nature of this correspondence, the contractor must do an extensive amount of custom writing. In addition, preparing responses to more complex letters often will require the contractor to access several ED data bases (see IV.A.3.b).

ED’s correspondence frequently relates to problems that began a number of years ago—a loan has defaulted years earlier, for example, or a student and school have a long-standing refund dispute. The contractor’s staff must, therefore, be completely knowledgeable about current and past Title IV regulations and policies. The contractor is responsible for keeping abreast of changing Title IV policies and procedures.

Meeting ED’s standards for preparing control and non-control correspondence means the contractor’s staff must not only choose the correct standard paragraphs, for example, but add to, or delete from, those paragraphs when necessary to create a response that flows logically from one sentence to another and from one paragraph to another. The contractor must tailor even “standard” paragraphs and “form” letters to each piece of correspondence, not repeating information the inquirer already knows, for example. In fact, for many responses, the contractor must develop and incorporate custom writing that responds to issues standard paragraph language or form letters do not cover. Custom language must be accurate, grammatically correct, logically linked, and completely responsive to the inquirer’s individual situation, answering all questions and addressing all issues. ED will determine whether the contractor’s language is accurate, grammatically correct, logically linked, and completely responsive to the inquirer’s individual situation.

v. Translating Correspondence into Languages Other than English

ED receives some correspondence from persons whose native language is not English. Because the non-English correspondence the contractor will receive usually will be in Spanish, ED already has a set of approximately 178 standard paragraphs and approximately 32 form letters translated into Spanish and available for the contractor.

For 1996, more than 80 form letters and approximately 178 responses using contractor-developed text were sent in response to Spanish correspondence; responses using contractor-developed text were expected to double for 1997. For 1996, approximately 35 form letters were translated into other languages.

2. Financial Aid Transcripts

If a student aid applicant/recipient transfers from one school to another or reenrolls in a school different from the one(s) previously attended, ED requires the student’s new school to request financial aid transcripts from all schools the student previously attended. The new school checks these transcripts (records of all federal student aid the student has received) to ensure the student does not receive more federal financial aid than he or she should. (ED’s student aid programs have annual and aggregate limits that cannot be exceeded.) Occasionally, schools have difficulty receiving transcripts and contact ED for assistance. In the past, ED’s contractor has checked into these situations and reported back to the inquiring schools. (Often, the contractor discovers that the school[s] the student previously attended has closed or no longer participates in Title IV programs. In either case, ED does not require financial aid transcripts.)

For 1996, ED received nearly 60,500 requests for financial aid transcripts; however, ED anticipates this number will drop significantly beginning in 1998-99: ED expects all postsecondary schools to access ED’s National Student Loan Data System (NSLDS) to receive federal financial aid information for students. It is possible, however, that the ESC will still need to handle some of these requests.

B. Personnel Requirements for Contractor Staff

1. Default Record

No member of the contractor staff shall be in default on any Title IV loan, including, but not limited to, Federal Family Education Loans (comprising Federal Stafford Loans, Federal PLUS Loans, and Federal Consolidation Loans); Federal Perkins Loans (including National Direct Student Loans and National Defense Student Loans); and William D. Ford Federal Direct Loans (comprising Federal Direct Stafford/Ford Loans, Federal Direct Unsubsidized Stafford/Ford Loans, Federal Direct PLUS Loans, and Federal Direct Consolidation Loans).

2. ED will approve all subcontractors the Editorial Services contractor hires.

3. All contractor personnel shall be located off site.

4. Minimum Qualifications

i. Project Director

The contractor’s Project Director shall have at least five years’ supervisory experience successfully managing a variety of work projects, some of which had simultaneous deadlines. The Project Director shall demonstrate successful experience in determining priorities, achieving goals, and accomplishing tasks on time; maintaining the highest standards of quality in work produced; and allocating appropriate resources to respond to large volumes of services provided. The Project Director shall demonstrate successful experience in managing personnel to accomplish required tasks and in addressing deficiencies and problems in a timely and effective manner. The Project Director also shall have a baccalaureate degree. The Project Director shall devote an adequate amount of time to this contract (at least 60 percent FTE).

The initial Project Director and all future Project Directors the contractor hires or assigns to this contract each shall provide a résumé demonstrating clearly that he or she meets the requirements discussed in the preceding paragraph. Each résumé also shall demonstrate clearly that each Project Director’s experience and duties relate directly to this SOW’s tasks.

ii. Mid-Level Supervisors

a. At least one mid-level supervisor shall have a baccalaureate degree and shall be thoroughly knowledgeable about federal student aid programs under Title IV of the Higher Education Act of 1965, as amended. The supervisor(s) also shall have at least two years’ experience answering a variety of highly technical questions about Title IV programs.

Each such supervisor and each such future supervisor the contractor hires or assigns to this contract shall provide a résumé demonstrating clearly that he or she meets the requirements discussed in the preceding paragraph. Each résumé also shall demonstrate clearly that each such supervisor’s experience and duties relate directly to this SOW’s tasks.

b. At least one mid-level supervisor shall have a baccalaureate degree; at least two years’ experience as a successful professional technical writer; the writing skills to produce written materials that are clear, accurate, grammatically correct, well-organized, and with logically linked sentences and paragraphs; and the ability to monitor and improve the writing and editing skills of subordinate staff.

Each such supervisor and each such future supervisor the contractor hires or assigns to this contract shall provide a résumé demonstrating clearly that he or meets the requirements in the preceding paragraph. Each résumé also shall demonstrate clearly that each such supervisor’s experience and duties relate directly to this SOW’s tasks. Each such supervisor shall attach to the résumé at least three samples of his or her original technical writing. Each sample shall be at least 1,000 words long. The contractor shall give these samples to ED for review when ED directs.

iii. Minimum Project Staff

Each writer on the project staff shall have a baccalaureate degree and at least one year’s experience as a successful professional technical writer. Each writer the contractor hires or assigns to this contract shall provide a résumé that demonstrates clearly that he or she meets the requirements just mentioned and that he or she has the writing skills to produce written materials that are clear, accurate, grammatically correct, well-organized, and with logically linked sentences and paragraphs. The résumé also shall demonstrate clearly that each writer’s experience and duties relate directly to this SOW’s tasks. Each writer shall attach to the résumé at least three samples of his or her original technical writing. Each sample shall be at least 1,000 words long. The contractor shall give these samples to ED for review when ED directs.

In addition to this staff, the contractor shall be able to obtain personnel with diverse qualifications on an as-needed basis.

The contractor’s Project Director and mid-level supervisors are key personnel.

C. Quality Assurance Surveillance Plan (QUASP)

ED will use a QUASP to monitor the contractor’s performance. ED will prepare the QUASP and will update it periodically if ED determines it necessary. (See the QUASP found elsewhere in this contract.)

IV. PERFORMANCE REQUIREMENTS SUMMARY

# PHASE A: PLANNING AND PREPARATION

IV.A.1: Defining Project Procedures; Producing a Procedures Manual and a Quality Control Plan

The contractor shall

a. upon contract award, ensure that the contractor’s Project Director shall review with the COTR all procedures related to the tasks this Statement of Work specifies.

b. develop, and submit to ED, a complete Procedures Manual (Manual) the contractor shall use in achieving the contract’s objectives. ED will review and approve the Manual before the contractor’s staff shall use it. Once ED has approved the Manual, the contractor shall implement it. The Plan’s supplements and revisions become ED’s property. The contractor shall prepare the Manual in loose-leaf format to fit into a ringed binder.

c. produce a final version of the Quality Control Plan (Plan) the contractor produced as part of its proposal. The contractor shall prepare the Plan in loose-leaf format to fit into a ringed binder. The final Plan shall ensure that quality control procedures are in place throughout the life of the contract. Once ED has approved the Plan, the contractor shall implement it.

The contractor’s plan shall include, but not be limited to, the following:

1. an inspection system covering all contract services. This system shall specify contract services the contractor shall inspect on scheduled and unscheduled bases and shall specify the individuals who shall do the inspections. The inspection system shall cover all equipment, all processes, and all products and shall describe how the contractor shall remedy problems.

2. a description of the relationship between overall work flow and quality control activities. The Plan shall identify quality control stations—points in the work flow where the contractor performs quality control activities and measurements—and shall identify those who shall perform the quality control activities and measurements. The Plan also shall describe how the contractor performs quality control activities at the various stations.

3. a description of how the contractor collects quality control performance data. The Plan also shall describe internal reporting procedures and procedures for reporting to ED on quality control.

4. a method of identifying deficiencies in the quality of services before the level of performance becomes unacceptable. The Plan shall include the provision that the contractor shall assign to other tasks those staff members falling short of standards this contract prescribes. The contractor shall give this staff additional training until the staff can meet contract standards. The Plan also shall ensure the contractor provides properly trained and fully successful replacement staff.

# IV.A.2: Participating In, and Providing, Training

The contractor shall

a. participate in training that ED and/or ED-provided trainers will conduct concerning the contract’s provisions. The training shall include, but not be limited to, one session of approximately five working days. ED’s topics for training will include, but not be limited to, information about Title IV student aid programs and ED data bases, high quality correspondence responses, and control mail response packages. ED will designate resource persons to assist the contractor in understanding OSFAP procedures. The contractor shall bill ED only for staff labor hours (at labor rates this contract specifies) for participating in training that ED and/or ED-provided trainers conduct. The contractor also shall bill for the cost of preparing ED information to disseminate to contractor staff unable to receive ED training, but only if ED and/or ED-provided trainers do not prepare such information.

b. ensure its project staff and mid-level supervisory staff are well-versed in the Title IV student aid programs by the start of Phase B. The contractor shall ensure that its staff absorbs ED materials listed in Section J and all other materials ED might provide during Phase A that supplement, or update, materials Section J lists. The contractor shall measure the effectiveness of its Title IV training by administering to the contractor’s project staff and mid-level supervisory staff pre- and post-tests the contractor shall develop and score. The COTR will approve these tests before the contractor shall administer them. The COTR also will review the test results. The contractor’s Project Director shall review the test results to ascertain the need for additional training and testing.

c. read sample correspondence ED will supply from correspondence files and prepare complete, accurate, and clear responses to those samples as practice for Phase B. In preparing responses, the contractor shall use ED’s current standard paragraphs and form letters that ED will provide, as well as original writing the contractor shall develop. ED will review the responses and discuss the results with contractor staff.

d. ensure that project staff and mid-level supervisory staff receive training on the requirements of the Privacy Act of 1974 and are thoroughly knowledgeable about the Privacy Act by the start of Phase B. The contractor shall measure the training’s effectiveness by administering to the contractor’s staff pre- and post-tests the contractor shall develop and score. The COTR will approve these tests before the contractor shall administer them. The COTR also will review the test results. The contractor’s Project Director shall review the test results to ascertain the need for additional training and testing.

# IV.A.3: Installing and Testing Equipment to Ensure Successful Contract Operation

The contractor shall

a. by the end of Phase A, have installed and completely tested all equipment necessary to ensure the successful performance of this contract. Such equipment shall include, but not be limited to, all necessary internal software.

b. identify the equipment the contractor needs for “read only” access to ED’s data bases. ED’s current data bases are

1. Central Processing System (CPS). This system is ED’s applicant data base and contains information about students who have applied for Title IV aid via the Free Application for Federal Student Aid (FAFSA). The contractor shall use this system to answer questions about FAFSA data and student eligibility.

2. Recipient and Financial Management System (RFMS). The contractor shall use this system’s data to answer inquiries about past and present Federal Pell Grant awards made to students.

3. Postsecondary Education Participants System (PEPS). This system is OSFAP’s management information system, containing data about postsecondary institutions. The contractor shall use this data base to answer requests for financial aid transcripts (see IV.B.10). The PEPS system has replaced the Institutional Data System (IDS). It is possible, however, that one IDS subsystem might still be operational at the beginning of Phase A; if so, the contractor also shall access the Default Management (Federal Family Education Loan [FFEL]) Subsystem, which provides the ability to identify schools with unacceptable student loan default rates. (ED does not allow schools to participate in Title IV programs if the student loan default rate of students who have graduated exceeds certain rates.) The contractor shall respond to inquiries about a school’s eligibility to participate in Title IV programs.

4. National Student Loan Data System (NSLDS). The NSLDS is a national data base of information about individual federal student loans and about other Title IV financial aid. ED uses NSLDS to pre-screen applications for Title IV aid, to support a variety of research functions aimed at improving program administration and student aid delivery, and to improve the efficiency of some aspects of the Title IV Delivery System through the application of automation and standardization. The contractor shall use this system to obtain information about student eligibility and student loan status.

5. Debt Management and Collection System (DCS)

i. Collections Subsystem. This subsystem consists of a series of on-line screens (available to loan collectors and researchers) that display data for use in communicating with debtors and updating collection activity on accounts. The contractor shall use these screens to retrieve account-level information for a specific debtor and determine the composition of debt types included in the debtor’s account. In this way, the contractor shall ascertain whether an inquirer has a file on this subsystem, that is, whether DCS holds the inquirer’s loan; if so, the contractor shall return that inquiry to ED. If ED does not hold the debtor’s loan(s), the contractor shall use this subsystem to obtain information about the debtor’s account and shall use that information in preparing responses.

ii. IRS Offset Subsystem. This subsystem identifies defaulted accounts that ED can certify, via magnetic tape, to the Internal Revenue Service (IRS) to include in the IRS Federal Tax Refund Offset Program. Through this program, ED provides certified debts that the IRS can collect by offsetting the debtor’s federal income tax refund, thereby reducing the outstanding balance due ED. The contractor shall use this subsystem to verify that a loan is in default and to determine who holds the loan—a guaranty agency or ED. The contractor also shall use this subsystem to determine if a student loan borrower’s federal income tax has been offset.

This subsystem also receives data from guarantee agencies so that their defaulted loans can be included in the certification process. Guarantee agency data are merged with ED records for certification to IRS. Offset information the IRS returns is then extracted and disseminated to the appropriate guarantee agencies.

iii. Research Subsystem. The Research Subsystem provides access to individual account and debt level information through online, menu-driven, query functions. The screens included in this subsystem allow users to view past, current, and projected financial information. The screens provide information such as debts owed, payments and other financial transactions applied to accounts, the method of applying these financial transactions, addresses that have been updated, data related to the program history of specific debts, account payoff amounts, and a history of collection agency referrals. The contractor shall use this information to answer questions about student loan accounts.

6. ED’s Web Site. ED’s web site (www.ed.gov) is an electronic source of information including, but not limited to, OSFAP regulations, news bulletins, Dear Colleague letters, other policy issuances, and other OSFAP program information. The contractor shall use ED’s web site to obtain updated student aid information. (The direct address for updated information is ifap.ed.gov.)

c. know what equipment ED will provide the contractor to connect with the data bases IV.A.3.b describes.

1. The primary means of communication with ED’s data bases will be via the Internet or remote dialin to ED’s Virtual Data Center (VDC) in Meridan, Connecticut. All electronic mail to and from ED will occur via the Internet. Alternatively, ED might furnish the contractor with either a remote dialin of sufficient bandwidth or with a WITS or FTS2000 data circuit. However, the contractor would have to conduct a traffic/bandwidth analysis and provide it to ED before ED would agree to provide a dedicated service of any type.

If ED does provide a data circuit, it will connect into the contractor’s network with a 10/100 MB ethernet connection. All equipment ED provides will be self-contained in a 19-inch rack mount cabinet; ED will be responsible only for the 24 x 7 operations of the data path. (Again, ED will provide this arrangement only if remote access via the Internet or remote dialin is not sufficient.) Due to security concerns, the contractor shall have its connections to the Internet secured with the use of an active “firewall” product (see IV.B.4 for more information about security requirements).

2. The network standard protocol ED uses is TCP/IP. Connections to mainframes use TN3270/TN3270E. For routing TCP/IP, ED’s standard routers are Cisco routers. Office automation servers are Windows NT. All data passed to and from ED’s computer systems will use TIV WAN standard data compression software, COM-PRESS. All systems connecting with ED’s computer resources shall be Year 2000 compliant. Desktop workstations’ client software and operating systems shall be Microsoft clients that are Year 2000 compliant also. ED will not use or support Microsoft Disk Operating System (DOS), Windows 3.1, Windows 3.11, or Windows for Workgroups.

3. ED’s Postsecondary Education Participants System (PEPS) uses a remote connectivity software called “REACHOUT” (by Stac Electronics) to communicate with a remote client. Through the remote client, the user may gain access via the Oracle Forms and Oracle Reports application. Currently, ED provides only remote dialup access; ED does not provide toll free numbers.

d. ensure it uses, at a minimum, the following software to connect to ED’s data bases:

1. a TN3270 emulator like Attachmate’s Extra! for Windows to communicate with all of ED’s “legacy” systems with which the contractor shall be concerned (that is, with the Central Processing System, Recipient and Financial Management System, National Student Loan Data System, and Debt Management and Collection System).

2. a remote connectivity software called “REACHOUT” (by Stac Electronics) to communicate with ED’s Postsecondary Education Participants System.

e. upon contract award, specify in writing the data circuit requirements to connect its office into ED’s Frame Relay network.

f. provide a network drawing of the contractor’s existing network connections, depicting clearly the contractor’s existing network layout and showing all external connections, routers/bridges and internal servers connected to the contractor’s network. The contractor shall identify TCP/IP addresses with each network device.

g. be responsible for its own internal connections, connections to any of its subcontractors, and Internet connections.

h. specify in writing router port requirements.

i. have in place a firewall for Internet access and shall employ, for its connection to ED, a firewall the National Computer Security Association has certified.

j. to access ED’s web site, have Internet access through an Internet Service Provider and a standard web browser. (ED’s current external Internet browser standard is Netscape 3.01 with the strong encryption key [128 bit]).

k. use basic office equipment to carry out this contract’s functions including, but not limited to

1. computers and printers sufficient to handle the correspondence and editorial support tasks this contract requires. The contractor shall be able to furnish documents in Macintosh versions of software that ED will specify. At the time ED gives an assignment to the contractor, ED might specify that the contractor shall produce a document involving a specific type of software. Also, ED reserves the right to require the contractor to create products involving as-yet-undeveloped software. Text and layout programs ED currently uses include, but are not limited to, Microsoft Word, PageMaker, DeltaGraph, FreeHand, Photoshop, and Illustrator.

2. at least one microfiche reader with printing capability for use as needed to handle inquiries that require examining individual applicant records. The microfiche reader(s) shall be capable of handling microfiche measuring approximately 4 1/2 inches x 5 3/4 inches or the metric equivalent.

3. at least one image workstation to access images of the Free Application for Federal Student Aid (FAFSA), that is, to read actual completed FAFSAs that federal student aid applicants have submitted to ED.

4. at least one photocopying machine necessary to perform this contract’s work.

5. at least one paper shredder to destroy confidential information.

6. at least one facsimile machine.

7. at least one date-stamp machine.

## IV.A.4: Meeting Security Requirements

The contractor shall

a. ensure that the local network used for this contract complies with the security requirements in ED’s Information Technology Security Program (ITSP) Manual and, where applicable, ED’s Information Technology Security Manual. The contractor also shall comply with procedures in the following documents:

1. U. S. Department of Education Standards

• “U.S. Department of Education Automatic Data Processing (ADP) Technical Control Handbook”

• “U.S. Department of Education Regulation 34”

• “U.S. Department of Education Personnel Security—Suitability Program,

Handbook #11”

2. Congressional Laws

• The “Privacy Act of 1974” (Public Law [PL] 93-579)

• The “Freedom of Information Act of 1974” (PL 93-502)

• The “Federal Managers’ Financial Integrity Act of 1983” (PL 97-255)

• The “Computer Fraud and Abuse Act of 1986” (PL 99-474)

• The “Computer Security Act of 1987” (PL 100-235)

3. Office of Management and Budget (OMB) Circulars

• OMB Circular No. A-130, Appendix III, “Security of Federal Automated

Information Systems”

• OMB Circular No. 90-08, “Guidance for Preparation of Security Plans for

Federal Computer Systems that Contain Sensitive Information”

4. Federal Information Processing Publications (FIPS PUBS)

• FIPS PUB 41, “Computer Security Guidelines for Implementing the Privacy Act of 1974”

• FIPS PUB 83, “Guidelines on User Authentication Techniques for Computer Network Access Control”

• FIPS PUB 87, “Guidelines for ADP Contingency Planning”

• FIPS PUB 112, “Password Usage”

• FIPS PUB 113, “Computer Data Authentication”

b. ensure that its systems security safeguards contain measures concerning

1. telecommunications, encryption, and firewalls—the contractor shall provide effective security measures to protect from unauthorized access the contracting local system used to access ED data bases. The contractor shall encrypt telecommunication lines that transmit sensitive data.

2. identification and authorization—the contractor shall ensure that the contracting local security system used to access ED data bases provides adequate user identification and authorization functionality. Identification shall be unique to each user, and the security contracting local system used

to access ED data bases shall limit users to only those classes of information or system access the users need to do their jobs.

3. passwords—in accordance with FIPS PUB 112, “Password Usage,” the following password parameters shall apply for the contracting local system used to access ED data bases:

i. The security management process the contractor shall use shall be capable of managing passwords of at least six alphanumeric characters and shall include at least one numeric value in the character string. The contractor shall ensure that the password’s length and makeup shall not show directly or indirectly on the log-in device. The contractor shall encrypt all passwords. The contractor shall be able to change the passwords at least once every 30 days. If such a change is not possible, the contractor shall explain why and shall request a waiver of the 30-day requirement.

ii. The security contracting local system shall notify the user automatically that his or her password has expired and shall specify the actions required to obtain a new password. The security contracting local system shall not allow users to reuse at least three previous passwords. Once a password expires, the security contracting local system shall lock the user’s account; only the security administrator of the contracting local system shall be able to reinstate access to the system.

4. sensitive data—the contractor shall ensure that it shall shred sensitive data in hard copy format when the data are no longer needed. (See IV.B.18.) When the contractor accesses or produces sensitive data from electronic media including, but not limited to, ED’s data bases, the contractor shall erase the data to prevent reuse or retrieval once data are no longer needed. In addition, the contractor shall ensure it prints sensitive data in a controlled area and shall ensure that persons in the controlled area shall be authorized to have access to the data being printed. Further, the contractor shall store all correspondence responses in an archive server, not on individual work stations, and shall ensure limited access to the archive server.

5. audit—the contractor shall provide an operating contracting local system (used to access ED data bases) that supports a security management audit trail. The system shall record, at a minimum, log-on attempts and failures and applicable commands or other related user activity. The contractor shall store the audit trail in the contracting local system used to access ED data bases or on tape. The contractor shall protect the audit trail from unauthorized access, modification, and destruction. The audit trail shall be completely recoverable without data loss.

c. implement effective physical security safeguards to ensure the protection of ED assets including, but not limited to, computer facilities, equipment, data, and personnel. The contractor shall provide security 24 hours a day. The contractor shall ensure that a controlled, limited-access environment exists in all areas where government data are maintained including, but not limited to, off-site storage facilities.

The contractor shall comply with the facility security requirements in the ITSP Manual.

d. ensure it complies with ED’s clearance requirements and procedures (as explained below) for all contractor and subcontractor personnel participating in designing, operating, and maintaining this contract. This compliance requirement applies to contractor and subcontractor personnel having access to facilities where ED data are serviced or stored. Requirements for personnel checks that these policies impose vary with the sensitivity of the data each employee handles and with the risk and magnitude of loss or harm associated with the type of position and access each employee has.

1. Personnel Clearance Requirements

i. The COTR is responsible for identifying by name all contract personnel and the contract labor categories of those contract personnel requiring access to ED systems. The COTR will ensure required paperwork is properly completed, reviewed for accuracy, and submitted to ED promptly before any contract employee works on sensitive parts of the contract.

ii. Contract personnel assigned to duties under this contract might be subject to ED investigation. ED’s investigation might include, but not be limited to, the following:

• Investigation of criminal record

• Checking references on previous employment

• Checking for defaulted student loans

• Previous security clearances

iii. After reviewing the position duties for this contract and related system access, if any, ED will assign the appropriate clearance levels for contractor personnel. Each security level has limitations on when a person may begin contract tasks after submitting the proper clearance packages.

2. Clearance Procedures

i. Contractor and subcontractor personnel shall complete and submit the required government forms based on level of clearance and job performed. A definition of the security levels follows:

a) High Risk (Level 6C)—High risk positions are those having potential for exceptionally serious impact because they involve duties especially critical to ED (for example, Project Director and security administrator).

b) Moderate Risk (Level 5C)—Moderate risk positions are those having the potential for moderate to serious impact (for example, persons who are responsible for directing, planning, designing, operating, or maintaining computer systems).

c) Low Risk (Level 1C)—Low-risk positions are those requiring access to computer systems (for example, application programmers).

d) Non-Disclosure Statement Positions (NS)—Depending on job responsibility and related limited systems access, signed copies of the “Privacy Act Statement” and “Declaration for Federal Employment” (OF-306) might be the only forms required. Individuals in this category perform duties that are closely monitored and supervised to ensure risk is limited (for example, data entry and documentation specialist).

ii. Should ED not require a contractor or subcontractor employee to undergo a background security screening, the following events shall occur:

a) ED must be confident that the contractor has adequate administrative and internal security controls in place to protect ED assets and information.

(1) Internal System Controls: In the process of defining positions personnel, the contractor shall establish controls such as “least privilege,” “separation of duties,” and “individual accountability.” “Least privilege” refers to granting contractor employees only the access to facilities and to ED systems needed to perform official duties. “Separation of duties” refers to dividing roles and responsibilities so that a single individual cannot subvert or control critical processes. “Individual accountability” refers to holding individual users responsible for their actions. Behavior on all the systems shall be according to established rules.

(2) Internal system controls shall address the requirements indicated in the ITSP Manual and OMB Circular A-130, Appendix III. The contractor shall identify in its Security Plan these controls and their functionality.

iii. The contractor shall complete the required clearance forms, as follows:

| Form | Title | Copies | High (6C) | Moderate (5C) | Low (1C) | NS |
| --- | --- | --- | --- | --- | --- | --- |
| OF- 306 | Declaration for Federal Employment | 2* | X | X | X | X |
| NS | Non-Disclosure/Privacy Act Statement | 1 | X | X | X | X |
| SF-85P | Questionnaire for Public Trust Positions | 2* | X | X |  |  |
| SF-85 | Questionnaire for Non-Sensitive Positions | 2* |  |  | X |  |
| FD-258 | Fingerprint Card | 1 | X | X | X |  |

* Original and one copy

iv. The following steps are required for submitting employee clearance documents, once clearance levels are established for the various contract positions and the COTR has approved them.

a) The contractor’s employees without previous clearance shall complete the required forms, as shown in the above table, based on the defined labor categories. (Note: Every employee must complete the Non-Disclosure/Privacy Act Statement and the OF 306.)

(1) The contractor shall describe each applicant’s various labor categories in sufficient detail to allow the COTR to decide which categories of employees need authorization for system access and, once employees have access, which would have the need or ability to bypass specific security controls. The ability and capability to bypass specific security controls is a major factor in determining any security clearance level.

(2) The COTR will require applicants for system access to fill out a Non-Disclosure/Privacy Act Statement and an OF 306.

(3) The COTR will check each applicant’s name and Social Security Number for defaulted student loans. If ED identifies the applicant as being in default, the COTR will forward the information to the Debt Collection Service for appropriate action. If ED identifies the applicant as suitable for system access, ED then will determine the level of each applicant’s access.

b) The contractor’s managers with current (non-departmental) or previous clearances (including departmental), who are required to obtain a clearance for employment on this contract, shall complete a letter, on contractor letterhead, that provides

Employee’s full name				Date and place of birth

Social Security Number		 		Type and level of security clearance

Employer name (at time of investigation)	Date of investigation

Contract number					Agency completing the investigation

c) Contractor employees with current or previous clearances who require upgrades due to changes in labor categories or system access shall provide additional paperwork, if necessary. The COTR will take the issue to the Computer Security Officer (CSO) for a ruling and a decision on what, if any, action is necessary.

d) If ED denies a required security clearance, the contractor employee shall be ineligible for assignment on this contract.

v. When the contractor removes employees from contract positions for any reason, the contractor shall

a) revoke all access authorizations and notify the COTR, within one working day, of the removal date and termination date. If termination is for cause, the contractor shall immediately revoke system access and follow up by notifying the COTR.

b) retrieve all keys, card keys, and badges allowing access to system facilities.

c) ensure terminated employees no longer have access to sensitive areas.

d) review with the departing employee the obligation to protect system, and ED Privacy Act, data and information.

e. submit a Security Plan (Plan) that meets all applicable ADP security requirements outlined in the ITSP Manual. The contractor shall prepare the Plan in loose-leaf format to fit into a ringed binder. The contractor shall submit one copy of the Plan to the COTR and one copy to the Contracting Officer.

The contractor shall implement the Plan, once ED has approved it, to ensure that security and Privacy Act requirements are maintained. The Plan shall include controls the contractor has established or must develop to maintain information integrity, availability, and confidentiality, as these apply to the contractor’s system.

The contractor shall prepare the Plan according to the ITSP Manual and OMB Bulletin 90-08.

1. The contractor’s Plan shall have, at a minimum, the following sections:

• Introduction

• Computer Security Overview

• Computer Security Management Approach

• Computer Operations

• Data Communication Operations

• Operating System Security

• Disaster Recovery Planning

• Contingency Planning

• Security Auditability

2. Additionally, the Plan shall incorporate facility layouts, drawings and inspections, and procedures.

f. prepare a Disaster Recovery Plan (Plan) for ED’s review and approval. The contractor shall prepare the Plan in loose-leaf format to fit into a ringed binder. The contractor shall give one copy of the final version of the Plan to the Contracting Officer and one to the COTR. The contractor shall implement the Plan, once ED has approved it, to ensure that services and functions will continue even if a major disaster renders a key operational facility unusable.

The contractor shall prepare the Plan according to the guidelines and procedures in FIPS Pub 87, “Guidelines for ADP Contingency Planning.”

1. Contingency Planning

i. The contractor shall include, at a minimum

a) procedures for responding to each type of disaster.

b) emergency response actions for the central site.

c) backup operations.

d) recovery operations—recovery operations shall include sufficient information to assure ED that at least 25 percent of the services under the ESC shall be restored within one working day, at least 50 percent of those services shall be restored within three working days, and 100 percent of those services shall be restored within five working days.

ii. In addition, the plan shall fully document the following:

a) possible alternate-site location(s)

b) procedures to move to the alternate site

c) procedures to demonstrate successfully the possible alternate site(s) and the site’s ability to support the ESC requirements

2. System Backup/Disaster Recovery

i. The contractor shall provide the hardware, software, and procedure for reliable backup and restoration of data stored. Specific requirements for data backup/recovery are as follows:

a) The backup system shall be able to fully back up/restore ESC data files in less than one hour.

b) The backup system shall be able to restore single and multiple files.

c) Backup software shall provide extensive error correction and detection.

ii. The contractor shall back up files incrementally on daily, weekly, and monthly bases. The contractor shall keep daily backups for at least a week, shall keep weekly backups for at least a month, and shall keep monthly backups for at least a year. The contractor shall provide off-site storage of all backup data.

### PHASE B: PRODUCTION

### IV.B.1: Answering Control Correspondence

The contractor shall

a. no sooner than two months after the date of Phase B startup, begin reviewing all correspondence the contractor retrieves from the Training and Program Information Division’s (TPID’s) correspondence pickup box—currently located in Room 3013, Regional Office Building 3 (ROB-3), 7th and D Streets, SW, Washington, DC—or from another location(s) ED might designate.

1. The contractor shall determine whether the subject matter is appropriate for TPID or whether the correspondence shall go to another ED office, ED contractor, federal agency, or another entity for response. If the contractor determines any entity other than TPID must respond, the contractor shall return the correspondence to the COTR, adding a notation to the correspondence indicating why the contractor is unable to respond.

2. The contractor shall forward, or return, original documents the correspondence might contain.

i. The contractor shall forward original FAFSAs and SARs to ED’s Central Processing System (to an address ED will provide), as long as ED’s processing deadline has not passed (that deadline is August 31 each year). The contractor shall indicate in the response the contractor prepares that the FAFSA and/or SAR has been forwarded. If the deadline has passed, the contractor shall include, as part of the response package the contractor prepares (see IV.B.1.o), the original FAFSAs and SARs and shall explain in the response why the materials are being returned.

ii. The contractor shall return to the COTR all other personal documents the correspondence might contain. The contractor also shall return to the COTR any correspondence containing checks, plus the checks themselves.

Although the contractor shall not begin screening correspondence sooner than two months after the date of Phase B startup, the contractor shall begin preparing responses to correspondence immediately on the date of Phase B startup.

b. use a date-stamp machine to record, on the correspondence tracking sheet, the date the contractor receives each piece of control correspondence.

c. contact a congressional office (for congressional correspondence) or the inquirer (when the correspondence is not from a member of Congress) when the following circumstances occur simultaneously: The correspondence does not contain, or is unclear about, information necessary to prepare a complete, accurate response, and the situation is of sufficient urgency to warrant contacting the appropriate party to obtain that information in the most expeditious way possible (including, but not limited to, using the telephone). Due to Privacy Act considerations, however, the contractor shall not use electronic mail (e-mail) to obtain information.

1. Examples of necessary information the correspondence might not contain include, but are not limited to, the inquirer’s or—in the case of correspondence from a member of Congress—the constituent’s Social Security Number, date of birth, loan type, and school attended. Another example is congressional correspondence that does not contain a properly authorized Privacy Act release form, allowing a Congressperson (or his or her constituent) to receive information on a student’s behalf.

2. A situation of sufficient urgency includes, but is not limited to, an inquirer who needs, by a certain date, information about student financial aid or a resolution to a student financial aid problem. (For example, an aid applicant might have a problem with his or her Student Aid Report [SAR], and the SAR deadline is soon approaching; the inquirer needs to submit the SAR by the deadline.) Another example of sufficient urgency is a politically sensitive letter; in such a case, ED will direct the contractor to reply quickly in a particular situation.

3. If a congressional office sends ED the inquiry, the contractor shall contact the congressional office to obtain the necessary information. If the White House refers the inquiry, or if the inquirer writes ED directly, the contractor shall contact the inquirer directly. If the contractor chooses to use the telephone as the method of contact, and the inquirer does not include his or her telephone number, the contractor shall call directory assistance to obtain the inquirer’s telephone number. If the contractor cannot obtain the correct number from directory assistance, the contractor shall reply to the inquirer in writing.

4. When the contractor makes a contact as described in this task, the contractor shall prepare a summary of the information the contractor obtained. The contractor shall include that summary as part of the response’s file box copy. (Section J makes available a sample file box copy.) The contractor’s summary shall contain legible, easily comprehensible information including, but not limited to, the correspondence control number; the date the contractor obtained the information; from whom the contractor obtained the information; and a description of the information the contractor gathered.

5. In cases such as, but not limited to, the SAR deadline situation described in paragraph 2 above, the contractor shall respond by telephone in place of a written response when a telephone response can answer the inquiry completely. The contractor shall first check with the COTR to determine whether a telephone response is sufficient. When the contractor responds by telephone instead of by written response, the contractor shall summarize information about the telephone conversation(s). The summary shall contain legible, easily comprehensible information including, but not limited to, the correspondence control number, the person(s) to whom the contractor’s staff spoke, the response the contractor’s staff gave the inquirer, and the date(s) the contractor’s staff made the call(s). The contractor shall attach the summary to the incoming correspondence and return both to ED.

d. access, when necessary, the Central Processing System (CPS) to determine what information a student has reported on his or her Free Application for Federal Student Aid (FAFSA). The contractor also shall be able to access an image of the FAFSA. The contractor shall access the CPS in situations that include, but are not limited to, the inquirer’s asking about a processing delay or stating that his or her FAFSA has been processed incorrectly and thus contains incorrect information. The contractor shall include in the response the information the contractor found when accessing this data base.

1. When answering correspondence from an inquirer questioning the amount of federal student aid received (or why he or she received no aid), the contractor shall include with the response’s file box copy certain printouts of the FAFSA transaction screen currently called, “Financial and Miscellaneous Screen.” The contractor shall include all such screen printouts for all FAFSA transactions relevant to preparing a complete, accurate response. The contractor shall include all appropriate FAFSA transactions not only from the current award year but also from relevant previous award years. The contractor shall continue this process if ED renames the FAFSA transaction screen or provides the information in some other electronic format.

2. Contractor staff who review a student aid applicant’s record and discuss it with anyone shall enter a notation on the data base telephone log line describing to whom the staff spoke and what the staff discussed.

e. generate a request, through the CPS, to send a duplicate Student Aid Report (SAR) to an inquirer who states he or she did not receive a SAR, but shall do so only when the contractor can tell that at least four weeks have passed since the inquirer submitted a FAFSA.

f. when necessary to prepare complete, accurate responses, access one or more of the other ED data bases IV.A.3.b describes. The contractor shall include in its responses all relevant information the contractor finds when accessing one or more of these data bases.

g. calculate accurately a student’s Expected Family Contribution (EFC) when the inquirer (or inquirer’s parent) does not understand why the inquirer is not eligible for federal student financial assistance or believes the assistance is not adequate. In preparing the calculation, the contractor shall use worksheets ED will provide. The contractor shall include the correct EFC calculation as part of the completed response.

h. conduct research, when necessary, to answer completely and accurately all issues and questions in correspondence including, but not limited to, correspondence involving casework. (See Section III A 1 iv of this SOW for a description of requirements for preparing casework responses; that section’s language is incorporated into this task by reference.) In evaluating its research findings, the contractor shall determine accurately whether it needs to do more research. If, in preparing any final response, the contractor realizes it needs to do more research to prepare a complete, accurate response, the contractor shall conduct all necessary followup research before submitting any final response to ED. As part of the response’s file box copy, the contractor shall include legible and easily comprehensible evidence of the research findings so that ED can compare the facts the contractor has uncovered with the completed response.

The contractor shall use its best judgment to obtain complete, accurate information in the most expeditious way possible including, but not limited to, using the telephone, facsimile machine, the Internet, and all other state-of-the-art technology.

i. summarize briefly and accurately in the response’s first paragraph the major issues the correspondence contains.

j. prepare complete, accurate, and clear responses. A “complete” response addresses each issue and each question in the current correspondence and, when relevant, incorporates all information from appropriate prior correspondence (see IV.B.1.v). An “accurate” response contains no typographical and spelling errors and no errors of fact or omission. A “clear” response links all sentences and all paragraphs so that the response presents information logically and smoothly with no confusion and ambiguity. The contractor shall ensure correct grammar and principles of clear writing as specified in the most current college edition of The American Heritage Dictionary (and other dictionaries ED might require the contractor to use in the future), Strunk and White’s The Elements of Style, The Chicago Manual of Style (14th edition and any subsequent editions), Words Into Type (12th edition and any subsequent editions), and other writing guides ED might require the contractor to use including, but not limited to, ED-developed style guides. (See IV.B.4.) Section III A 1 iv of this SOW provides additional information about what ED expects in its responses; that section’s language is incorporated into this task by reference. In preparing responses, the contractor also shall follow ED preferences, defined as instructions UNIQUE TO ED that do NOT involve the good grammar principles, good writing principles, and other instructions contained in all dictionaries and guides ED might require the contractor to follow.

k. conduct quality control checks—before responses reach ED for review—to ensure responses are complete, accurate, and clear, according to the principles in paragraph j above. Mid-level supervisors shall ensure the contractor’s writing staff sees, and learns from, all changes resulting from quality control checks.

l. prepare responses using the approved signature block of the correct ED official (Secretary; Assistant Secretary; Chief Operating Officer; Director, Training and Program Information Division [Division Director]); and the approved signature block of other ED officials when ED directs. The tracking sheet attached to the correspondence shows the title of the official for whom the contractor shall prepare the response. The contractor shall store and use the correct ED stationery that ED will supply. For Division Director letters and, when ED directs, for letters for other officials, the contractor shall use the correct scanned-in signature ED will provide.

m. enclose all information materials relevant to the issues and inquiries in the correspondence. Information materials include, but are not limited to, ED student aid publications, the FAFSA, ED fact sheets, and Title IV regulations. The contractor shall include such materials whenever the correspondence contains general questions about federal student aid including, but not limited to, what types of federal student aid exist, how to apply for federal student aid, why the inquirer did not receive federal student aid (or why he or she did not receive sufficient aid), whether the inquirer can receive deferments or forbearance on federal student loans, and what options are available to repay defaulted federal student loans. The contractor shall explain in the response what materials are enclosed. The contractor shall bill ED for including materials with completed responses only under this sub-task and shall not also bill under IV.B.12.

n. in the following cases, provide completed responses on PC-formatted disks (in addition to hard copy) and in IBM-compatible format: when the contractor prepares responses for the Secretary’s signature and, when ED directs, when the contractor prepares certain responses for the Assistant Secretary’s signature.

o. prepare a response package, enclose all parts of that package in either a red or a dark blue pocket folder (unless ED later approves different colors or different methods of furnishing responses), and send each folder to ED. The contractor shall forward to ED in red pocket folders all responses prepared for signature above the Division Director level (that is, responses prepared for the Secretary, Assistant Secretary, or Chief Operating Officer). The contractor shall forward to ED in dark blue pocket folders (1) responses prepared for the Division Director’s signature (which will be the vast majority of responses) and (2) responses prepared for other ED officials when ED directs. The contractor shall supply all pocket folders.

1. A response package shall consist of

i. the written response to the inquirer prepared on the appropriate ED-supplied stationery.

ii. an 8 1/2 inch x 11 inch (or metric equivalent) clear, plastic cover labeled “Executive Correspondence” (that ED will supply), placed over the original response.

iii. the correct number of copies of the response correctly marked with the name of each copy’s recipient in the upper right hand corner of page one of the copy.

iv. correct information materials as described in IV. B.1.m.

v. an ED-franked envelope of a size suitable to the contents being mailed (size 4 inches x 9 1/2 inches or 9 1/2 inches x 12 inches or their metric equivalents). ED will supply all envelopes. The 4 inch x 9 1/2 inch envelope will be a window envelope, and the inquirer’s correct address shall be completely and clearly visible through the window. The 9 1/2 inch x 12 inch envelope shall show the inquirer’s complete and correct address.

The contractor shall assemble the response package properly (see Section J).

2. The contractor shall place the following information on the front of each response package folder: the last name of the member of Congress (if any) who has sent the correspondence on behalf of a constituent, followed by the last name of the constituent (or of the inquirer, if no member of Congress is involved), followed by the correspondence control number, followed by the due date from the correspondence tracking sheet. The contractor shall ensure that all information is legible and contained in an area measuring no larger than 3 inches x 2 inches (or the metric equivalent).

p. forward to ED completed responses within three working days after the contractor receives the correspondence. For example, if the contractor receives correspondence on Monday, the contractor shall return the completed response to ED no later than Thursday, assuming that all four days are work days. (For responses prepared in languages other than English, see IV.B.8.)

ED establishes the following exceptions to turnaround times when the contractor conducts research to prepare responses:

1. If preparing a complete, accurate response requires the contractor to conduct research (see IV.B.1.h), the contractor shall complete the response and return it to ED within six working days after the contractor receives the correspondence. If, according to the date on the correspondence tracking sheet, the correspondence is already overdue when the contractor receives it, the contractor shall first prepare an interim response for the inquirer, acknowledging the delay, and shall deliver the interim to ED within one working day after the contractor receives the overdue correspondence. The final response shall contain, in the first paragraph, a reference to the fact that the inquirer has already received an interim on this subject.

2. If the contractor cannot complete a response within six working days after receiving the correspondence because the contractor cannot obtain all the information necessary from sources within or outside ED, the contractor shall inform the COTR (within the six-working-day period) about the steps the contractor has taken to obtain the information and the reasons the contractor has been unsuccessful. The contractor then shall prepare an interim response for the inquirer, acknowledging the delay, and shall deliver the interim to ED within one working day after discussing the correspondence with the COTR. The contractor then shall have up to four working days, in addition to the original six working days, to complete the final response and return it to ED. The final response shall contain, in the first paragraph, a reference to the fact that the inquirer has already received an interim on this subject.

q. shall incorporate correctly all ED comments and corrections ED might provide as the result of reviewing the contractor’s responses. Mid-level supervisors shall ensure the contractor’s writing staff sees, and learns from, the comments and corrections ED makes. If ED has to return correspondence for the contractor to redo, ED will consider the lapsed time a contractor-caused delay.

r. re-mail responses, without charging ED mailing costs, if responses are returned to ED because the contractor erred in preparing mailing addresses.

s. return telephone calls from inquirers who have questions and concerns about responses the contractor has prepared. The contractor shall provide all appropriate additional information to inquirers. The contractor also shall prepare and return to ED a legible, easily comprehensible summary of the results of the contractor’s call

t. in response to occasional “write-in” campaigns from the general public about a particular issue, develop form letter responses with personalized addresses when ED directs.

u. prepare responses that require inserting referral data of, but not restricted to, five lines of text that ED will provide. Examples of such data include, but are not limited to, ED regional office addresses, ED’s Office of Inspector General address, foreign consulate addresses, and other federal agencies’ addresses. The contractor shall include the insertions in an otherwise regular control response and shall make sufficient copies of the response so that ED can send a copy to the referral address, if appropriate. For some offices outside ED that ED will specify, the contractor also shall include an envelope of a size suitable to the contents being mailed; the envelope shall show the referral address.

v. respond promptly to detailed questions from ED about individual pieces of correspondence and shall, when ED directs, retrieve from the contractor’s files and forward to ED the complete files for any responses the contractor has prepared in the preceding two calendar years. The complete file for a response shall consist of a copy of the incoming correspondence; any related documentation including, but not limited to, a research summary; and the outgoing response. The contractor also shall retain in its files, for two calendar years from the date of contractor receipt, all correspondence (paper and electronic) the contractor has received from, or that relates to, an inquirer, even if the contractor did not prepare a response to that correspondence.

IV.B.2: Answering Non-Control Correspondence (Paper and Electronic Mail [E-Mail])

The contractor shall

a. no sooner than two months after the date of Phase B startup, begin reviewing all correspondence the contractor retrieves from

• ED’s Post Office Box 84, Ben Franklin Station, 12th Street and Pennsylvania Avenue, NW, Washington, DC.

• the Training and Program Information Division’s (TPID’s) correspondence pickup box, currently located in Room 3013, Regional Office Building 3 (ROB-3), 7th and D Streets, SW, Washington, DC.

• ED’s SFA e-mail box.

• another location(s) ED might designate.

1. The contractor shall determine whether the subject matter is appropriate for TPID or whether the correspondence shall go to another ED office, ED contractor, federal agency, or another entity for response.

i. If the contractor determines any ED office other than TPID must respond,

a) the contractor shall redirect paper correspondence by (1) addressing a messenger envelope with the correct ED office name and room number and (2) returning the correspondence to TPID via the contractor’s courier. The courier shall place the messenger envelope in TPID’s outgoing mail tray in Room 3013, ROB-3 (or in some future room ED might specify).

b) the contractor shall redirect e-mails to the appropriate ED e-mail addresses ED will provide.

ii. If the contractor determines any entity other than an ED office must reply, the contractor shall return paper correspondence to the COTR and shall redirect e-mails to ED’s SFA e-mail box. The contractor shall add a notation, to both paper and e-mail correspondence, indicating why the contractor is unable to respond.

2. The contractor shall refer to the COTR all correspondence the contractor is unable to answer or refer to another entity. Such correspondence includes, but is not limited to

i. correspondence that must be converted to control correspondence (examples include, but are not limited to, correspondence addressed to ED’s Chief Operating Officer or to TPID’s Division Director and correspondence of a politically sensitive nature).

ii. paper correspondence containing original personal documents including, but not limited to, checks and personal identification materials.

ED might use the P.O. Box 84 address as a central point for receiving certain correspondence from postsecondary schools or libraries, such as, but not limited to, answers to ED questionnaires. The contractor also shall forward such correspondence to the COTR.

3. Privacy Act restrictions prohibit the contractor from providing certain information to inquirers via e-mail, including, but not limited to, applicant and borrower record information. In these cases, the contractor shall not return such e-mail correspondence to ED but shall send an e-mail to the inquirer, requesting him or her to resubmit to ED all issues in a signed letter.

4. The contractor shall forward original FAFSAs and SARs to ED’s Central Processing System (to an address ED will provide), as long as ED’s processing deadline has not passed (that deadline is August 31 each year). The contractor shall indicate in the response the contractor prepares that the FAFSA and/or SAR has been forwarded. If the deadline has passed, the contractor shall return original FAFSAs and SARs to inquirers with an appropriate form letter ED will specify.

Although the contractor shall not begin screening correspondence sooner than two months after the date of Phase B startup, the contractor shall begin preparing responses to correspondence immediately on the date of Phase B startup.

b. use a date-stamp machine to record, on each piece of paper correspondence, the date the contractor receives the correspondence.

c. contact the inquirer, in certain cases involving paper correspondence only, to obtain additional information before preparing a response.

1. The contractor shall contact the inquirer when the following circumstances occur simultaneously: The correspondence does not contain, or is unclear about, information necessary to prepare a complete, accurate response, and the situation is of sufficient urgency to warrant contacting the inquirer to obtain that information in the most expeditious way possible (including, but not limited to, using the telephone). Due to Privacy Act considerations, however, the contractor shall not use electronic mail (e-mail) to obtain information.

i. Examples of necessary information the correspondence might not contain include, but are not limited to, the inquirer’s Social Security Number, date of birth, loan type, and school attended. Another example is correspondence that does not contain a properly authorized Privacy Act release form, allowing an inquirer to receive information on a student’s behalf.

ii. A situation of sufficient urgency includes, but is not limited to, an inquirer who needs, by a certain date, information about student financial aid or a resolution to a student financial aid problem. (For example, an aid applicant might have a problem with his or her Student Aid Report [SAR], and the SAR deadline is soon approaching; the inquirer needs to submit the SAR by the deadline.)

iii. If the contractor chooses to use the telephone as the method of contact, and the inquirer does not include his or her telephone number in the correspondence, the contractor shall call directory assistance to obtain the inquirer’s telephone number. If the contractor cannot obtain the correct number from directory assistance, the contractor shall reply to the inquirer with a paper response.

2. When the contractor makes a contact as described in this task, the contractor shall prepare a summary of the information the contractor obtained. The contractor shall retain that summary as part of the response’s file. The contractor’s summary shall contain legible, easily comprehensible information including, but not limited to, the date the contractor obtained the information; from whom the contractor obtained the information; and a description of the information the contractor gathered.

3. In cases such as, but not limited to, the SAR deadline situation described in paragraph ii above, the contractor shall respond by telephone in place of a written response when a telephone response can answer the inquiry completely. When the contractor responds by telephone instead of by written response, the contractor shall summarize information about the telephone conversation(s). The summary shall contain legible, easily comprehensible information including, but not limited to, the person(s) to whom the contractor’s staff spoke, the response the contractor’s staff gave the inquirer, and the date(s) the contractor’s staff made the call(s). The contractor shall retain the summary, the incoming correspondence, and the completed response in the contractor’s non-control correspondence files.

d. access, when necessary, the Central Processing System (CPS) to determine what information a student has reported on his or her Free Application for Federal Student Aid (FAFSA). The contractor also shall be able to access an image of the FAFSA. The contractor shall access the CPS in situations that include, but are not limited to, the inquirer’s asking about a processing delay or stating that his or her FAFSA has been processed incorrectly and thus contains incorrect information. The contractor shall include in the response the information the contractor found when accessing this data base.

All contractor staff who review a student aid applicant’s record and discuss it with anyone shall enter a notation on the data base telephone log line describing to whom the staff spoke and what the staff discussed.

e. generate a request, through the CPS, to send a duplicate Student Aid Report (SAR) to an inquirer who states he or she did not receive a SAR, but shall do so only when the contractor can tell that at least four weeks have passed since the inquirer submitted a FAFSA.

f. when necessary to prepare complete, accurate responses, access one or more of the other ED data bases IV.A.3.b describes. The contractor shall include in its responses all relevant information the contractor finds when accessing one or more of these data bases.

g. calculate accurately a student’s Expected Family Contribution (EFC) when the inquirer (or inquirer’s parent) does not understand why the inquirer is not eligible for federal student financial assistance or believes the assistance is not adequate. In preparing the calculation, the contractor shall use worksheets ED will provide. The contractor shall include the correct EFC calculation as part of the completed response, which shall be a paper response.

h. conduct research, when necessary, to answer completely and accurately all issues and questions in correspondence including, but not limited to, correspondence involving casework. (See Section III A 1 iv of this SOW for a description of requirements for preparing casework responses; that section’s language is incorporated into this task by reference.) In evaluating its research findings, the contractor shall determine accurately whether it needs to do more research. If, in preparing any final response, the contractor realizes it needs to do more research to prepare a complete, accurate response, the contractor shall conduct all necessary followup research before sending out any final response. As part of the response’s file, the contractor shall retain legible and easily comprehensible evidence of the research findings so that ED may compare the facts the contractor has uncovered with the completed response.

The contractor shall use its best judgment to obtain complete, accurate information in the most expeditious way possible including, but not limited to, using the telephone, using the facsimile machine, the Internet, and all other state-of-the-art technology.

i. summarize briefly and accurately in the response’s first paragraph the major issues the correspondence contains.

j. prepare complete, accurate, and clear responses. A “complete” response addresses each issue and each question in the current correspondence and, when relevant, incorporates all information from appropriate prior correspondence (see IV.B.2.s). An “accurate” response contains no typographical and spelling errors and no errors of fact or omission. A “clear” response links all sentences and all paragraphs so that the response presents information logically and smoothly with no confusion and ambiguity. The contractor shall decide correctly whether a form letter response answers completely and accurately all issues and questions the correspondence contains. If not, the contractor shall incorporate standard paragraphs and/or shall include custom writing the contractor shall develop. The contractor shall ensure correct grammar and principles of clear writing as specified in the most current college edition of The American Heritage Dictionary (and other dictionaries ED might require the contractor to use in the future), Strunk and White’s The Elements of Style, The Chicago Manual of Style (14th edition and any subsequent editions), Words Into Type (12th edition and any subsequent editions), and all other writing guides ED might require the contractor to use including, but not limited to, ED-developed style guides. (See IV.B.4.) Section III A 1 iv of this SOW provides additional information about what ED expects in its responses; that section’s language is incorporated into this task by reference. In preparing responses, the contractor also shall follow ED preferences, defined as instructions UNIQUE TO ED that do NOT involve the good grammar principles, good writing principles, and other instructions contained in all dictionaries and guides ED might require the contractor to follow.

k. conduct quality control checks to ensure responses are complete, accurate, and clear, according to the principles in paragraph j above. The contractor shall ensure that it spot checks form letter responses and reviews all responses containing (1) standard paragraphs the contractor has incorporated and (2) custom writing the contractor has developed. Mid-level supervisors shall ensure the contractor’s writing staff sees, and learns from, all changes resulting from quality control checks.

l. for paper correspondence, use the scanned signature of the Director, Division of Training and Program Information and shall store and use the correct ED stationery that ED will supply. For e-mail correspondence, the contractor shall use a standard signature block ED will provide.

m. for paper responses, enclose all information materials relevant to the issues and inquiries in the correspondence. Information materials include, but are not limited to, ED student aid publications, the (FAFSA), ED fact sheets, and Title IV regulations. The contractor shall include such materials whenever the correspondence contains general questions about federal student aid including, but not limited to, what types of federal student aid exist, how to apply for federal student aid, why the inquirer did not receive federal student aid (or why he or she did not receive sufficient aid), whether the inquirer can receive deferments or forbearance on federal student loans, and what options are available to repay defaulted federal student loans. The contractor shall explain in the response what materials are enclosed. The contractor shall bill ED for including materials with completed responses only under this sub-task and shall not also bill under IV.B.12.

In answering e-mail correspondence, when the contractor determines that ED materials are necessary, the contractor shall instruct inquirers to obtain those materials from, when possible, ED’s web site (the contractor shall include web address[es] ED will provide). If materials are not available on ED’s web site, the contractor shall provide the Federal Student Aid Information Center’s toll-free number in the response.

n. send out completed responses within two working days after the contractor receives the correspondence. For example, if the contractor receives correspondence on Monday, the contractor shall send out the completed response no later than Wednesday, assuming that all three days are work days. (For responses prepared in languages other than English, see IV.B.8.) The contractor shall not send preliminary, or interim, responses except in cases involving research/casework responses for e-mail (see paragraph 1 i below).

1. ED establishes the following exceptions to turnaround times when the contractor conducts research to prepare responses:

i. If preparing a complete, accurate response requires the contractor to conduct research (see IV.B.2.h), the contractor shall send out completed responses to inquirers within five working days after the contractor receives the correspondence. For e-mail only, the contractor shall send an interim response to the inquirer within one working day after the contractor receives the inquirer’s e-mail, explaining that the contractor requires more than two working days to respond because the contractor is conducting research. The final e-mail response shall contain, in the first paragraph, a reference to the fact that the inquirer has already received an interim on this subject.

ii. If the contractor cannot complete a response within five working days after receiving the correspondence because the contractor cannot obtain all the information necessary from sources within or outside ED, the contractor shall prepare an interim response for the inquirer, acknowledging the delay. The contractor shall send the interim to the inquirer within one working day after discovering the contractor needs additional time. The contractor then shall have up to three working days, in addition to the original five working days, to send out the final response. The final response shall contain, in the first paragraph, a reference to the fact that the inquirer has already received an interim on this subject.

2. For e-mail responses, the contractor shall, when ED directs, forward electronic courtesy copies and/or blind copies to up to three ED staff members.

o. for e-mail responses that come back to the contractor as undeliverable (but solely because of factors the contractor cannot control), send the response a second time. If the second response comes back to the contractor as undeliverable, the contractor shall not attempt to send another e-mail response. If the inquirer included a regular mailing address as part of the e-mail correspondence, the contractor shall convert the e-mail response to a paper response and shall mail it to the inquirer. The contractor also shall keep a record in its files that it tried to send an e-mail response twice and that both e-mails were undeliverable.

p. shall prepare and send a revised response to an inquirer if ED discovers an error of fact or omission when ED does its surveillance of completed non-control responses. In such cases, the contractor’s mid-level supervisors shall ensure the contractor’s writing staff sees, and learns from, the corrections ED makes. If ED has to return correspondence for the contractor to redo, ED will consider the lapsed time a contractor-caused delay.

q. re-send responses (and re-send paper responses without charging ED mailing costs) if responses are returned to ED because the contractor erred in preparing the mailing address.

r. return telephone calls from inquirers who have questions and concerns about responses the contractor has prepared. The contractor shall provide all appropriate additional information to inquirers.

s. respond promptly to detailed questions from ED about individual pieces of correspondence and shall, when ED directs, retrieve from the contractor’s files and forward to ED the complete file for any response the contractor has prepared

1. in the preceding six months, for correspondence NOT related to application processing concerns. Because the contractor cannot provide e-mail responses related to application processing concerns (ED requires a signed letter from the inquirer), the contractor shall retain all e-mail correspondence for not more than six months.

2. in the preceding two calendar years, for correspondence related to application processing concerns.

The complete file for a response shall consist of a copy of the incoming correspondence and a notation of which form letter the contractor used to respond, if the contractor used a form letter. If the response consisted of a modified form letter, that is, the contractor incorporated standard paragraphs and/or custom writing, the complete file shall consist of a copy of the incoming correspondence; any related documentation including, but not limited to, a research summary; and the outgoing response.

The contractor also shall retain in its files, for either six months or two calendar years, as specified above, all correspondence (paper and electronic) the contractor has received from, or that relates to, an inquirer, even if the contractor did not prepare a response to that correspondence.

### IV.B.3: Accessing the Contractor’s Data Base(s) and E-Mail History

The contractor shall

a. establish a data base(s) for all control and non-control correspondence and ensure ED will access the data base(s) from TPID’s site. ED will be able to read and print out all correspondence and all responses the contractor has prepared during, at a minimum, the previous six months. (See IV.B.2.s for retention periods.)

b. tag or label each non-control response in the data base(s) so that when ED accesses the data base(s) from TPID’s site, ED will distinguish the type of non-control response the contractor has prepared. The types shall include, but not be limited to, form letters, interims, custom letters (involving standard paragraph selection and/or custom writing), and casework—or research—responses.

c. ensure ED will obtain from the data base(s) all information necessary to respond to questions on the status of all correspondence received between the previous six months, at a minimum, and the preceding two calendar years, at a maximum. (See IV.B.1.v and IV.B.2.s.)

d. ensure ED will have access to the contractor’s data base(s) from 6:00 a.m. through 8:00 p.m., Eastern time, Monday through Friday—minus any down time the contractor requires to perform basic maintenance and upgrades to the contractor’s data base(s) and/or network(s).

e. bill ED for a one-time charge to connect TPID to the contractor’s data base(s) and shall bill ED thereafter only when the contractor corrects problems and provides necessary upgrades that are solely related to TPID’s connection to the contractor’s data base(s). The contractor shall not bill ED for fixing, upgrading, and maintaining the data base(s) itself.

f. connect TPID to the contractor’s data base(s) using the most expeditious method.

g. ensure that both ED and the contractor have full access to ED’s SFA e-mail box. The contractor shall ensure, at a minimum, that ED staff can observe, from TPID’s site, the date e-mail from the public comes in to the SFA e-mail box and the date the contractor sends out responses to those e-mails or refers e-mails to another ED office. The contractor also shall ensure that ED can read incoming e-mails and their corresponding responses.

# IV.B.4: Supplying Staff with Dictionaries and Writing/Style Guides

The contractor shall supply the following dictionary and writing/style guides for its writing staff to use: the most current college edition of The American Heritage Dictionary, (and other dictionaries ED might require in the future), Strunk and White’s The Elements of Style, The Chicago Manual of Style (14th edition and any subsequent editions), Words Into Type (12th edition and any subsequent editions), and all other writing guides ED might require the contractor to use including, but not limited to, ED-developed style guides. The contractor shall provide sufficient copies of all dictionaries and guides to ensure a ratio of one set of dictionaries and guides for every four writers, assuming the writing staff consisted of at least four persons. The contractor shall bill ED directly for these dictionaries and guides, except the contractor shall not bill for guides ED develops for the contractor to use.

### IV.B.5: Providing Courier Service

The contractor shall

a. provide courier service between ED and the contractor’s site twice daily, except on federal holidays and except for other times when ED directs. The courier service shall pick up from TPID incoming control and non-control paper correspondence and shall deliver to TPID completed responses. The courier service also shall deliver to TPID certain misdirected correspondence (see IV.B.1.a and IV.B.2.a). The courier service also shall pick up and deliver other materials ED will specify. The contractor shall ensure that—each working day—the courier shall arrive at ED no later than 10:00 a.m. and shall arrive again between 2:00 p.m. and 3:00 p.m. Pickup and delivery from TPID shall occur in Room 3013, Regional Office Building 3 (ROB-3), 7th and D Streets, SW, Washington, DC, or in another room ED might designate in the future.

b. also pick up non-control correspondence daily at Post Office Box 84, Ben Franklin Station, 12th Street and Pennsylvania Avenue, NW. This pickup shall occur either immediately before, or immediately after, the courier’s morning pickup at TPID.

c. provide an additional courier delivery and pickup on days when ED notifies the contractor before 1:00 p.m. that ED requires this service.

d. ensure that all couriers understand completely the pickup and delivery system and that couriers shall not require instructions from ED staff.

IV.B.6: Preparing Control and Non-Control Correspondence Reports and Other Reports

The contractor shall

a. provide, on a weekly basis, complete and accurate verbal counts of control and non-control correspondence answered during the previous week.

b. provide accurate weekly written counts of all correspondence—control and non-control—received, pending (including an explanation of why the correspondence is pending), and completed. Within these broad categories, the contractor shall provide counts on specific categories of correspondence including, but not limited to, standard inquiries, e-mails, form letters, casework, revised responses, P.O. Box 84 correspondence received, ROB-3 correspondence received, and misdirected correspondence. The contractor also shall include information on correspondence by subject category including, but not limited to, application processing questions, closed school issues, defaulted loans, financial aid eligibility, and loan repayment questions.

c. provide complete and accurate monthly written reports on the number and types of interim responses prepared, including information such as, but not limited to, the inquirer’s name, the nature of the inquiry, and the reason the contractor could not complete the responses within the time frames this SOW specifies (see IV.B.1.p and IV.B.2.m).

d. provide complete monthly written reports about complaints the contractor observes in correspondence including, but not limited to, complaints about specific postsecondary institutions, guarantee and service agencies, and the National Student Loan Data System (NSLDS).

e. provide a monthly report on the results of the contractor’s ongoing quality improvement efforts. Such reports shall include, but not be limited to, quality improvement efforts in answering control and non-control correspondence for the previous month.

f. submit monthly an accurate written inventory of materials that ED is responsible for providing including, but not limited to, ED materials used as enclosures and ED materials mailed upon request.

g. when ED directs, use charts and graphs to illustrate clearly, and enhance, the reports the contractor prepares.

### IV.B.7: Updating Standard Paragraphs, Form Letters, and Fact Sheets

The contractor shall

a. update annually the existing set of standard paragraphs and fact sheets used to respond to control and non-control correspondence. The contractor shall keep current on legislative and policy changes to the Title IV programs so the contractor can make annual changes easily and promptly. Keeping current about Title IV program changes means the contractor shall review materials including, but not limited to, applicable statutes, regulations, and Dear Colleague letters, as these materials become available. The contractor shall assimilate this material thoroughly to revise standard paragraphs and fact sheets completely, accurately, and clearly (see IV.1.j and IV.2.j). The contractor also shall update program-specific material, including, but not limited to, year changes (such as changing 1999-00 to 2000-01), addresses, and telephone numbers.

b. when giving ED the annual update of standard paragraphs and fact sheets, ensure ED receives a hard copy set of the updates, showing each paragraph’s and each fact sheet’s layout as it shall appear in its final page layout format. ED will review the standard paragraphs and fact sheets and send any revisions to the contractor. The contractor shall make the revisions, returning to ED the original marked-up version of ED’s revisions plus a clean, typed copy, again showing each paragraph’s and each fact sheet’s layout as it shall appear in its final page layout format. When ED has approved the final round of revisions, the contractor shall incorporate them promptly into the permanent set of standard paragraphs and fact sheets.

c. after revising standard paragraphs and fact sheets completely, accurately, and clearly, update the form letters based on the standard paragraph and fact sheet revisions. The contractor shall give ED a hard copy set of the updated form letters, showing each form letter’s layout as it shall appear in its final format. ED will review the form letters and send any revisions to the contractor. The contractor shall make the revisions, returning to ED the original marked-up version of ED’s revisions plus a clean, typed copy, again showing each form letter’s layout as it shall appear in its final page layout format. When ED has approved the final round of revisions, the contractor shall incorporate them promptly into the permanent set of form letters.

d. shall provide standard paragraphs, fact sheets, and form letters on disk in Macintosh format at the time the contractor sends the initial annual revisions and again when the contractor has completed the final set of standard paragraphs, fact sheets, and form letters.

e. prepare annually an index of standard paragraphs and form letters that shall consist of a list of standard paragraphs and form letters deleted since the previous year and a brief description of each current standard paragraph and form letter. The description shall include, but not be limited to, the old paragraph and old form letter numbers, the new paragraph and new form letter numbers, and summaries of each current standard paragraph and form letter by subject matter. (See Section J for information on a sample index.)

f. prepare complete, accurate, and clear updates to individual standard paragraphs, fact sheets, and form letters throughout the year to reflect current program rules, regulations, and procedures, and all other necessary changes (see paragraph a of this task). When submitting updates, the contractor shall give ED a hard copy set of the updated standard paragraphs, fact sheets, and form letters, showing each standard paragraph’s, each fact sheet’s, and each form letter’s layout as it shall appear in final copy. ED will review the updates and send any revisions to the contractor. The contractor shall make the revisions, returning to ED the original marked-up version of ED’s revisions plus a clean, typed copy, again showing the standard paragraph’s, fact sheet’s, and form letter’s layout as it shall appear in its final page layout format. When ED has approved the final round of revisions, the contractor shall incorporate them promptly into the permanent set of standard paragraphs, fact sheets, and form letters.

g. revise standard paragraphs, form letters, and fact sheets when ED directs. The contractor shall incorporate ED revisions promptly into the permanent set of standard paragraphs, form letters, and fact sheets.

### IV.B.8: Preparing Correspondence Responses in Languages Other Than English

The contractor shall

a. prepare complete, accurate, and clear responses to correspondence the contractor receives in Spanish. (See IV.B.1.j and IV.B.2.j for definitions of “complete,” “accurate,” and “clear.”) For control correspondence, the contractor shall prepare responses in both Spanish and in English. For paper non-control correspondence, the contractor shall prepare responses in Spanish and, when ED directs, in English. If the contractor receives e-mails prepared in Spanish, the contractor shall not reply by e-mail but shall instead send a paper response in Spanish. (If the inquirer does not provide a regular mailing address in the e-mail, the contractor shall prepare an e-mail response in English and include a request for a mailing address in Spanish. The contractor shall prepare this request in RTF format in Spanish and send it as an attachment with the e-mail. When the contractor receives the inquirer’s regular mailing address, the contractor shall prepare a paper response in Spanish.) The contractor shall meet the same quality standards and same turnaround times required for preparing control and non-control responses in English (see IV.B.1 and IV.B.2).

b. prepare complete, accurate, and clear responses to correspondence the contractor receives in languages other than English and Spanish. (See IV.B.1.j and IV.B.2.j for definitions of “complete,” “accurate,” and “clear.”) For control correspondence, the contractor shall prepare responses in the inquirer’s language and in English. For paper non-control correspondence, the contractor shall prepare the responses in the inquirer’s language and, when ED directs, in English. If the contractor receives e-mails prepared in foreign languages other than Spanish, the contractor shall not reply by e-mail but shall instead send a paper response in the inquirer’s language. (If the inquirer does not provide a regular mailing address in the e-mail, the contractor shall prepare an e-mail response in English and include a request for a mailing address in the inquirer’s language. The contractor shall prepare this request in RTF format in the inquirer’s language and send it as an attachment with the e-mail. When the contractor receives the inquirer’s regular mailing address, the contractor shall prepare a paper response in the inquirer’s language.) The contractor shall meet the same quality standards required for preparing control and non-control responses in English (see IV.B.1 and IV.B.2). The contractor shall send out complete responses in foreign languages other than Spanish within seven working days after the date the contractor receives the correspondence.

### IV.B.9: Translating into Spanish, and Preparing Layout for, Certain ED Publications

The contractor shall translate into clear and accurate Spanish the publications Funding Your Education and the Free Application for Federal Student Aid (FAFSA). The contractor shall accurately proofread and edit the publications the contractor translates. The contractor shall prepare correct layout for the translated publications, using desktop publishing, and shall forward the completed layout to ED for review. The contractor shall furnish the layout in Macintosh format and shall prepare a hard copy version of these publications when ED directs. The contractor shall make revisions when ED directs. The contractor shall prepare a final camera ready version of the publications and an electronic copy of the camera ready version in both desktop publishing and Portable Document Format (PDF) formats.

### IV.B.10: Requesting Financial Aid Transcripts

The contractor shall

a. respond to requests from schools having difficulty receiving financial aid transcripts from other schools. Because the other school(s) often has closed, the contractor shall verify whether a school has closed by accessing the Postsecondary Education Participants System (PEPS).

b. for schools requesting financial aid transcripts, complete a “Financial Aid Transcript Status” form that ED will provide (for a sample form, see Section J). The contractor shall send this completed form to schools in response to their inquiries. The contractor shall photocopy this form as needed to maintain the contractor’s supply. (The contractor shall bill for this photocopying only under IV.B.20.) The contractor shall date-stamp this form before sending it to a school requesting financial aid transcript information.

c. shall maintain copies of all incoming requests and outgoing “Financial Aid Transcript Status” forms for six months from the date the contractor mailed the completed forms to schools.

# IV.B.11: Updating the OSFAP Regulations Compilation

The contractor shall update annually the existing compilation of all OSFAP student aid regulations. The contractor shall ensure it incorporates all Title IV regulations correctly into the compilation. The contractor also shall include, at the end of each regulation section, a notation showing changes to the regulations and the effective dates of those changes. The contractor also shall include appendices that list new regulations issued and that summarize the changes those regulations make. The contractor shall provide a hard copy and an electronic version of the compilation. ED will specify the format for the electronic version.

# IV.B.12: Mailing Materials

The contractor shall

a. mail single copies of ED publications and other materials to individual inquirers upon their request. ED will supply the contractor with appropriate publications and other materials that the contractor shall store at the contractor’s site. The contractor shall include a form letter with each mailing, listing what is included. The contractor also shall keep in its files all incoming requests the contractor receives for ED publications and other materials. The contractor shall date-stamp each request with the date the contractor received the request and shall keep a copy of the form letter that accompanied the mailing. The form letter shall show the date the contractor mailed the materials. The contractor shall ensure that ED can access the contractor’s data base and determine what materials the contractor has mailed within the previous two months.

b. ensure it addresses each envelope correctly. The contractor shall, without charging ED mailing costs, re-mail materials returned because the contractor did not address the envelope correctly.

### IV.B.13 Updating the Procedures Manual and the Quality Control Plan

The contractor shall

a. when ED determines necessary, but not more frequently than every six months during the life of the contract, supplement and revise the Procedures Manual (Manual) and Quality Control Plan (Plan) the contractor prepared in final in Phase A (see IV.A.1.b and IV.A.1.c). The supplements and revisions shall reflect accurately new procedures the contractor shall henceforth follow. Once ED has approved supplements and revisions, they become ED’s property. The contractor shall prepare updates in loose-leaf format to fit into a ringed binder.

b. adhere to Manual and Plan changes the COTR will issue in the form of memoranda to the contractor at times other than at a six-month updating interval. The contractor shall treat these memoranda as amendments to the Manual and/or Plan and shall incorporate the memoranda’s instructions in the Manual and/or Plan at the next occurring six-month interval.

### IV.B.14: Updating the Security Plan

The contractor shall update the Security Plan it produced in Phase A (see IV.A.4.e) whenever changes in government regulations systems occur. ED will alert the contractor when ED discovers a change in government regulations systems. The contractor shall prepare updates in loose-leaf format to fit into a ringed binder.

### IV.B.15: Updating and Implementing the Disaster Recovery Plan

The contractor shall

a. update the Disaster Recovery Plan (Plan) the contractor produced in final in Phase A (see IV.A.4.f) at least annually, but only when the Plan requires a major change including, but not limited to, a change in emergency procedures, a change in the Disaster Recovery Center’s (alternate work site’s) location, a change in the emergency contract services provider, a significant change in business/computer processing, and a significant change resulting from a simulated or “live” test at the Disaster Recovery Center (see b and c below). The contractor shall prepare updates in loose-leaf format to fit into a ringed binder.

b. conduct an annual test at the Disaster Recovery Center. The test shall simulate all procedures necessary to transfer this contract’s services and functions to another fully operational site should a disaster occur at the contractor’s original site. ED will attend the simulated test; the contractor shall establish a date and time for the test that is acceptable to ED.

c. once during the first three years of the ESC, conduct a “live” test at the Disaster Recovery Center. During the “live” test, the contractor shall carry out, instead of simulating, all procedures necessary to transfer this contract’s services and functions to another fully operational site should a disaster occur at the contractor’s original site. ED will attend the live test; the contractor shall establish a date and time for the test that is acceptable to ED.

d. document, and report to ED, all test results and shall recommend changes, if necessary, to correct problems the contractor encounters during the simulated and live Disaster Recovery Center tests. The contractor shall revise the Plan to incorporate those changes. The contractor shall bill for all reports only under IV.B.6 and shall not also bill under this task.

# IV.B.16: Updating Network Drawings

The contractor shall update the network drawings of the contractor’s network connections whenever the contractor adds new devices or connections to the network.

# IV.B.17: Maintaining Access to Different Data Bases

If ED computer system contractors change during the ESC, the contractor shall maintain access to two different data bases per ED computer system—for all periods when different data bases exist—for as long as ED requires. The overlap shall ensure the Editorial Services contractor shall respond to all public inquiries without interruption.

# IV.B.18: Maintaining Systems Security Safeguards

The contractor shall

a. immediately update authorization information for new users of the contracting local security system used to access ED data bases. The contractor shall prepare weekly reports showing all new users the contractor has added during the week. The contractor shall bill for these reports only under IV.B.6 and shall not also bill under this task.

b. update the contracting local security system used to access ED data bases upon termination and reassignment of employees and changes in employees’ job responsibilities. The contractor shall prepare weekly reports showing all employees the contractor has terminated and reassigned during the week. The contractor shall bill for these reports only under IV.B.6 and shall not also bill under this task.

c. ensure that its security contracting local system shall notify users automatically that their passwords have expired and shall specify the actions required to obtain new passwords. The contractor shall change users’ passwords at least once every 30 days or at the appropriate interval if ED has granted the contractor a waiver (see IV.A.4.b.3.i). The contractor shall ensure that its security contracting local system shall not allow users to reuse at least three previous passwords. Once a password expires, the contractor shall ensure that its security contracting local system shall lock the user’s account; only the security administrator of the contracting local system shall be able to reinstate access to the system. The contractor shall prepare monthly reports showing how many users on the contractor’s system have expired passwords, were unsuccessful logging on at any time, or attempted to invoke commands or functions in the systems that are prohibited by the users’ assigned user profiles. The contractor shall bill for these reports only under IV.B.6 and shall not also bill under this task.

d. print sensitive data in a controlled area and shall ensure that persons in the controlled area shall be authorized to have access to the data being printed. Further, the contractor shall store all correspondence responses in an archive server, not on individual work stations, and shall ensure limited access to the archive server.

e. ensure that when the contractor removes employees from contract positions for any reason, the contractor shall

1. revoke all access authorizations and notify the COTR of employees’ removal dates and termination dates. If termination is for cause, the contractor shall immediately revoke employees’ system access and shall follow up by notifying the COTR.

2. retrieve all keys, card keys, badges, and all other means of allowing access to system facilities.

3. ensure terminated employees no longer have access to sensitive areas.

4. review with departing employees the obligation to protect ED computer system, and Privacy Act, data.

The contractor shall prepare weekly reports showing all employees whom the contractor has removed (if any) during the week, their user IDs, and the dates the contractor has removed the employees or, in cases of removal for cause, the date the contractor decided to remove the employees. The contractor shall bill for these reports only under IV.B.6 and shall not also bill under this task.

# IV.B.19: Producing Labels

The contractor shall, when ED directs, produce labels including, but not limited to, address labels. For sets of address labels, ED will submit addresses in handwritten, rough-typed draft or in computer printout format. The contractor shall proofread the labels to ensure complete accuracy.

### IV.B.20: Photocopying

The contractor shall photocopy various materials including, but not limited to, correspondence, responses to correspondence, student aid fact sheets, worksheets, Dear Colleague letters, and charts. The contractor shall be capable of segregating all photocopying the contractor does for the ESC from all other photocopying the contractor does for all other clients.

### IV.B.21: Shredding/Erasing Materials

The contractor shall shred or otherwise erase all appropriate materials including, but not limited to, control correspondence files that are more than two years old, non-control correspondence (NOT related to application processing concerns) that is more than six months old, non-control correspondence (related to application processing concerns) that is more than two years old, and all sensitive data including, but not limited to, Privacy Act-related data. When accessing or producing sensitive data from electronic media including, but not limited to, ED’s data bases, the contractor shall erase the data to prevent reuse or retrieval once data are no longer needed.

### IV.B.22: Participating In, and Providing, Training

The contractor shall

a. participate in ED and/or ED-provided training when ED directs. Training might involve ED and/or ED-provided trainers traveling to the contractor’s site to brief the contractor’s staff. ED also might provide training through means including, but not limited to, conference calls and written instructions. ED’s training will include, but not be limited to, providing ED computer system updates, improving proofreading skills, selecting correct standard paragraphs and form letters, and linking sentences and standard paragraphs correctly. ED also might provide information on new laws, regulations, policies, and other information ED deems important. ED or an ED-provided trainer will give the contractor at least two weeks’ notice before arriving at the contractor’s site to provide training.

1. The contractor shall ensure that any staff not attending ED’s training receives ED’s information in writing if ED and/or an ED-provided trainer does not provide written materials.

2. The contractor shall bill ED only for staff labor hours (at labor rates this contract specifies) for participating in training ED and/or ED-provided trainers conduct. The contractor also shall bill for the cost of preparing ED information in writing to disseminate to contractor staff unable to receive ED training, but only if ED and/or ED-provided trainers do not prepare such information in writing.

b. train its staff throughout the life of the contract when the contractor shall determine, and when ED directs, that any contractor staff needs training. The contractor shall provide training on topics including, but not limited to, improving editorial skills. This topic shall include, but not be limited to, proofreading, selecting correct standard paragraphs and form letters, linking sentences and standard paragraphs correctly, and improving the contractor staff’s custom writing. The contractor also shall provide training on Title IV program information and procedures and on quality control expectations. ED will provide suggestions for training when ED deems appropriate.

c. shall, when ED directs, ensure the contractor’s staff understands and retains all training by administering to its staff pre- and post-training tests the contractor shall develop, administer, and score. The COTR will approve these tests before the contractor shall administer them. The COTR might monitor the administration and scoring of the pre-and post-tests and will review the test results. The contractor’s Project Director also shall review the test results.

### IV.B.23: Participating in Conference Calls

Appropriate contractor staff including, but not limited to, the contractor’s Project Director shall participate in conference calls with the COTR and other appropriate ED staff to discuss issues related to the ESC’s operation. ED will hold these conference calls at least weekly. The contractor shall bill ED only for staff labor hours (at labor rates this contract specifies) for participating in conference calls.

IV.B.24: Assisting During Transition Period

The contractor shall

a. assist ED in making the transition to a successor contract. A transition period shall begin 60 to 30 days before the production phase begins at the successor contractor’s site. The previous contractor shall perform certain functions during the transition period including, but not limited to

1. working with ED staff and with the successor contractor’s staff to ensure a smooth and orderly transition. For example, the previous contractor shall provide the successor contractor with materials including, but not limited to, disks on which the previous contractor has stored standard paragraphs, form letters, and procedural and training manuals. ED will return to the previous contractor any contractor-owned materials on which government-owned information was stored after the successor contractor has copied the materials and information or converted them to the successor contractor’s type of storage. The previous contractor shall ensure it removes all government-owned information from contractor-owned materials.

2. delivering to an ED site(s), that ED will determine, all materials used in the performance of the previous Editorial Services Contract. These materials include, but are not limited to, all equipment (except leased equipment), computer files, computer programs and listings, control records, reports, and other data. Materials the previous contractor collected in the performance of the ESC shall be the

government’s property; the contractor shall not use these materials for purposes other than those described in this contract. ED’s contracting officer will notify the previous contractor of disposal procedures for all government materials.

b. retain all correspondence files through the end of the transition period.

SCHEDULE OF DELIVERABLES

Description	Task	Quantity	When

Procedures Manual	IV.A.1. b	One	Within 15 working days

after contract award

Quality Control Plan	IV.A.1.c	Two	Within 15 working days

(final)			 after contract award

Staff training pre- and 	IV.A.2. b	One each	Within 20 working days

post-tests—ED review 			after contract award

Staff training pre- and	IV.A.2. b	One each	Within 30 working days

post-tests—first test		per staff 	after contract award; 				member	scores to ED within three

working days after contractor

administers first test

Staff training pre- and	IV.A.2.b	One each	Within three working days

post-tests—second test:		per staff 	after contractor administers

for staff not receiving		member	first test; scores to ED within

at least 95 percent on			three working days after con-

first test			tractor administers second test

Staff training pre- and 	IV.A.2.b	One each	Within 10 working days

post-tests—third test:		per staff 	after contractor administers

for staff not receiving		member	second test; scores to ED within

at least 95 percent on			three working days after con-

second test			tractor administers third test

Sample correspondence	IV.A.2. c	50	Within 40 working days

replies 			after contract award

Privacy act training pre- 	IV.A.2.d	One each	Within 45 working days

and post-tests—ED			after contract award

review

Privacy Act training pre- 	IV.A.2.d	One each	Within 55 working days after

and post-tests—first test		per staff	contract award; scores to ED 			member	within three working days

after contractor administers				first test

Description	Task	Quantity	When

Privacy Act training pre- 	IV.A.2.d	One each	Within three working days

and post-tests—second 		per staff	after contractor administers

test: for staff not receiv-		member	first test; scores to ED within

ing at least 95 percent			three working days after

on first test			contractor administers second

test

Privacy Act training pre- 	IV.A.2.d	One each	Within three working days

and post-tests—third test:		per staff	after contractor administers

for staff not receiving at		member	second test; scores to ED within

least 95 percent on second			three working days after

test			contractor administers third

test

Installing equipment	IV.A.3.a	As needed	By the end of Phase A

necessary to operate

contract

Supply data circuit 	IV.A.3.e	One set of	Within 20 working days after

requirements		require-	contract award

ments

Network drawing of	IV.A.3.f	One set of	Within 20 working days after

contractor’s existing		require-	contract award

network connections		ments

Router port requirements	IV.A.3.h	One set of	Within 20 working days after

require-	contract award

ments

Security Plan	IV.A.4.e	Two	Within 30 working days

after contract award

Disaster Recovery Plan	IV.A.4.f	Two	Within 30 working days

after contract award

Completed control	IV.B.1.p	Any	Within three working days

responses—to ED			after receipt of correspondence

Interim for correspondence	IV.B.1.p	Any	Within one working day after

already overdue—to ED			receiving overdue correspon-				dence

Description	Task	Quantity	When

Completed responses	IV.B.1.p	Any	Within six working days

requiring research/			after receipt of correspondence;

casework—to ED			if contractor cannot obtain in-				formation, response is due 				within up to four additional 				working days after original six 				working days

Interim for correspondence	IV.B.1.p	Any	Within one working day         not completed within six 			after discussing correspondence

working days—to ED			with COTR

Revisions of control	IV.B.1.q	Any	Within two working days after

responses			receipt of ED’s revisions

Sending completed 	IV.B.2.n	Any	Within two working days

non-control  			after receipt of correspondence

correspondence

responses

For e-mail, interim to	IV.B.2.n	Any	Within one working day after inquirer for responses			receipt of inquirer’s e-mail

not able to be completed

within two working days

because research is needed

Completed 	IV.B.2.n	Any	Within five working days

responses requiring			after receipt of correspondence;

research/casework—			if contractor cannot obtain in-

to inquirer			formation, response is due 				within eight working days af-				ter receipt of correspondence

Interim for correspondence	IV.B.2.n	Any	Within one working day after not completed within five			discovering additional time is

working days—to inquirer			required to respond

Courier service	IV.B.5	Daily	Twice daily in morning and  				afternoon, unless ED specifies

otherwise

Description	Task	Quantity	When

Correspondence	IV.B.6	At least	Written—no later than each

reports		two 	Tuesday; Verbal—each Friday;

weekly; at 	Monthly/Interims—within

least two 	three working days after end of

monthly	previous month; Monthly/

Complaints—within three 				working days after end of

previous month; Monthly/

Quality Control Report—

within five working days after

end of previous month; 					Monthly/materials inven-				tory—within five working days 				after end of previous month

Updating standard	IV.B.7	Annually,	Annually—by February 1;

paragraphs and fact 		as needed,	Once sets are final, changes will sheets		and when	be incorporated within 10 			ED	working days after ED’s final 			directs	approval. As needed—within

five working days after obtain-				ing updated information. 				When ED directs—within three 			working days after receiving 				ED’s revisions.

Updating form letters	IV.B.8	Annually,	Annually—within seven

as needed,	working days after the date

and when	standard paragraphs and fact

ED	sheets are final. Once set 				directs	is final, changes will be incor-				porated within 10 working 				days after ED’s final approval.

As needed—within five work-				ing days after obtaining           				updated information. When 				TPID directs—within three

working days after				 		receiving ED’s revisions

Description	Task	Quantity	When

Annual index of	IV.B.7.e	Annually	Within 12 working days after

standard paragraphs			form letters are in final

and form letters

Preparing 	IV.B.8.a	Any	Same turnaround times as

correspondence			specified for control and

responses in Spanish			non-control responses in

English

Preparing 	IV.B.8.b	Any	Within seven working dayscorrespondence			after receipt of correspondence

responses in languages

other than English and

Spanish

Translating 	IV.B.9	Two	Within 20 working days after

publications into 			date contractor receives

Spanish and preparing			publication to translate

layout

SFA regulations	IV.B.11	Annually	Draft by March 1; final by

compilation			April 1

Updates of Procedures	IV.B.13	As needed	Not more than every six Manual and Quality			months, when ED determines

Control Plan			necessary

Updates of Security	IV.B.14	As needed	When changes in government

Plan			regulations occur

Updating Disaster	IV.B.15.a	As needed	At least annually, but only

Recovery Plan			when major change occurs

Simulated test at	IV.B.15.b	Annually	Within 12-month period

Disaster Recovery

Center

Live test at	IV.B.15.c	One	During first three years of con-

Disaster Recovery			tract

Center

Reports of tests at	IV.B.15.d	One	Within 10 working days after

Disaster Recovery		report	each test occurs

Center		per test

Description	Task	Quantity	When

Updating network	IV.B.16	As needed	When contractor adds new de-

drawings			vices or connections to network