# ESEA FLEXIBILITY MONITORING REPORT FOR THE

# CONNECTICUT STATE DEPARTMENT OF EDUCATION

## Overview Of ESEA Flexibility Monitoring

The U.S. Department of Education (ED) is committed to supporting State educational agencies (SEAs) as they implement ambitious reform agendas through their approved ESEA flexibility requests.  Consistent with this commitment, ED has developed a monitoring process that is designed to both ensure that each SEA implements its plan fully, effectively, and in a manner that is consistent with its approved request and the requirements of ESEA flexibility, as well as support each SEA with technical assistance to help ensure its implementation increases the quality of instruction and improves student achievement for all students in the State and its local educational agencies (LEAs).  Through this process, ED aims to productively interact with SEAs and shift from a focus primarily on compliance to one focused on outcomes.

For the 2012–2013 school year, ED has divided its ESEA flexibility monitoring process into three components, which are designed to align with the real-time implementation occurring at the SEA, LEA, and school levels and be differentiated based on an SEA’s progress and depth of work:

- Part A provided ED with a deeper understanding of each SEA’s goals and approaches to implementing ESEA flexibility and ensured that each SEA had the critical elements of ESEA flexibility in place to begin implementation of its plan in the 2012–2013 school year.  Part A was conducted through desk monitoring.

- Parts B and C, which are under development, will include a broader look at an SEA’s implementation of ESEA flexibility across all three principles, including its transition to college- and career-ready standards, its process for developing and implementing teacher and principal evaluation and support systems, and follow-up monitoring on the implementation of interventions in priority and focus schools.  Parts B and C reviews also will include a closer examination of the use of annual measureable objectives (AMOs), graduation rate targets, and other measures to drive supports and incentives in other Title I schools.  In addition, Parts B and C monitoring will address select unwaived Title I requirements and any “next steps” identified in the ESEA Flexibility Part A Monitoring Report.  These reviews will be conducted through a combination of on-site monitoring, desk monitoring, and progress checks that will be differentiated based on an individual SEA’s circumstances and request.  The format of future reports may vary from Part A.

ED will support each SEA in its implementation of ESEA flexibility across all three monitoring components and will work with each SEA to identify areas for additional technical assistance.

This ESEA Flexibility Part A Monitoring Report provides feedback to the Connecticut State Department of Education (CSDE) on its progress in implementing the components of ESEA flexibility identified in the document titled ESEA Flexibility Part A Monitoring Protocol to ensure the SEA implements ESEA flexibility fully, effectively, and in a manner that is consistent with the SEA’s approved request and the requirements of ESEA flexibility.  This report is based on information provided through SEA-submitted documentation, a monitoring call conducted with CSDE staff on September 13, 2012 and an exit conference held on October 2, 2012.  Generally, this report does not reflect steps taken by the SEA after the exit conference.

The report consists of the following sections:

- Highlights of CSDE’s Implementation of ESEA Flexibility.  This section identifies key accomplishments in the SEA’s implementation of ESEA flexibility as of the SEA’s monitoring call on September 13, 2012.

- Summary of CSDE’s Implementation of ESEA Flexibility and Next Steps.  This section provides a snapshot of the SEA’s progress in implementing each component of ESEA flexibility or unwaived Title I requirement based on the evidence CSDE described during its monitoring phone call on September 13, 2012; through written documentation provided to ED; and any further clarifications provided by the SEA during its exit conference phone call on October 2, 2012.  Where appropriate, this section also includes a set of “next steps” that were discussed with the SEA during its exit conference phone call, to ensure that the SEA implements the components of ESEA flexibility consistent with the principles and timelines in ESEA Flexibility and the CSDE’s approved request.

## Highlights Of CSDE’s Implementation Of Esea Flexibility

- Based on information provided during the monitoring conference phone call and through written documentation, CSDE’s work implementing ESEA flexibility includes the following key accomplishment:

- Including more students in its accountability system by lowering its n-size and creating a high-needs subgroup.

## Summary Of CSDE’s Progress Implementing ESEA Flexibility And Next Steps

### Principle 2: State-Developed Differentiated Recognition, Accountability, and Support

| Component 2.A | Develop and implement beginning in the 2012–2013 school year a system of differentiated recognition, accountability, and support for all LEAs in the State and for all Title I schools in these LEAs. |
| --- | --- |
| Summary of Progress | CSDE indicated during its initial monitoring call that it ran its system of differentiated recognition, accountability, and support using 2011-2012 data in order to identify priority, focus, and reward schools and to place each school in the State into one of five categories—Excelling, Progressing, Transition, Review, and Turnaround—based on an index that includes student achievement, gains in student achievement, graduation rate, and the percentage of students meeting the State’s highest performance level. CSDE explained that it did not face specific issues running its new system. CSDE also reported that the use of its high-needs subgroup, which includes English Learners, students with disabilities, and students eligible for free- and reduced-price lunch, captured more students than were previously included in its accountability system. On September 21, 2012, CSDE indicated that the use of its high-needs subgroup, coupled with lowering its n-size from 40 students to 20 students, resulted in additional schools receiving an accountability determination. |
| Next Steps | None. |

| Assurance 7 | Report to the public its lists of reward schools, priority schools, and focus schools at the time the SEA is approved to implement flexibility, and annually thereafter, it will publicly recognize its reward schools as well as make public its lists of priority and focus schools if it chooses to update those lists. |
| --- | --- |
| Summary of Progress | CSDE reported that it hosted a conference call for reporters interested in the list of priority and focus schools and has made these lists available to the media upon request. CSDE also reported that two of its 54 identified focus schools had closed. Nevertheless, CSDE stated that it will ensure that it identifies at least 10 percent of its Title I schools as focus schools. During its exit conference on October 2, 2012, CSDE reported that it had 541 Title I schools, rather than 530 Title I schools, as it had initially indicated in its ESEA flexibility request. As such, CSDE indicated that it would identify additional schools in order to ensure that it identifies at least 5 percent of its 541 Title I schools as priority schools and at least 10 percent of its 541 Title I schools as focus schools. Following its exit conference, CSDE contacted ED to report that, as a direct result of the disruption caused by Hurricane Sandy and other delays, it required an extension from its previously agreed upon reward, priority, and focus school lists publication date of November 2, 2012. CSDE stated that it would publish its reward, priority, and focus school lists on or before November 30, 2012. On November 30, 2012, CSDE published its reward, priority, and focus school lists at: http://www.sde.ct.gov/sde/cwp/view.asp?a=2683&Q=334526 (valid as of February 28, 2013). |
| Next Steps | To ensure that the SEA publicly reports its lists of reward, priority, and focus schools, CSDE will: identify at least five percent of its Title I schools as priority schools identify at least 10 percent of its Title I schools as focus schools finalize its identification of reward schools on or before November 30, 2012 provide final lists of its reward, priority, and focus schools to ED on or before November 30, 2012 publicize its final lists of reward, priority, and focus schools on or before November 30, 2012 ED confirmed on November 30, 2012 that CSDE published its lists of reward, priority, and focus schools. |

| Component 2.D | Effect dramatic, systemic change in the lowest-performing schools by publicly identifying priority schools and ensuring that each LEA with one or more of these schools implements, for three years, meaningful interventions aligned with the turnaround principles in each of these schools beginning no later than the 2014–2015 school year. |
| --- | --- |
| Summary of Progress | During our monitoring call, CSDE reported that during the 2012–2013 school year, 19 of CSDE’s 27 priority schools are implementing interventions. CSDE refers to these schools as turnaround schools. Eighteen are schools receiving School Improvement Grant (SIG) funds to implement one of the four SIG intervention models. In one additional non-SIG school, Harding High School, CSDE stated that it intends to implement interventions aligned with the turnaround principles this year. According to CSDE, 18 of the 19 priority schools are implementing interventions in 2012–2013. Of these schools, 13 are SIG-implementing schools that are in their third year of the grant; five are SIG-implementing schools that are in their second year of the grant; and one school is implementing interventions aligned with the turnaround principles. CSDE reported that all schools in both SIG cohorts are on track in their implementation and have implemented all necessary components of their models, including teacher evaluation systems tied to student achievement. CSDE stated, however, that it is possible that some of the SIG-implementing schools might be planning to implement different SIG models in the 2012–2013 school year. CSDE addresses challenges in implementation in its SIG schools through monthly monitoring and meetings of the SIG External Advisory Council, which brings together districts, schools, and consultants to solve problems and share effective practices. CSDE intends to implement in the remaining eight priority schools in the 2013–2014 school year. |
| Next Steps | In order to ensure that implementation of meaningful interventions aligned with all of the turnaround principles takes place in all priority schools for at least three years, ED will revisit, during Part B monitoring, the status of implementation at Harding High School and will review evidence and timelines related to this implementation. |

| Component 2.E | Work to close achievement gaps by publicly identifying Title I schools with the greatest achievement gaps, or in which subgroups are furthest behind, as focus schools and ensuring that each LEA implements interventions, which may include tutoring or public school choice, in each of these schools based on reviews of the specific academic needs of the school and its students beginning in the 2012–2013 school year. |
| --- | --- |
| Summary of Progress | During its monitoring call, CSDE indicated that its focus schools would complete their root cause analyses, develop their intervention plans, and submit these intervention plans to CSDE’s Commissioner in October, 2012. CSDE further indicated that these plans would be reviewed and subsequently implemented in December in all focus schools. Finally, CSDE indicated that it will provide redesign and reform support to districts and professional development to teachers specific to subgroup interventions. During its monitoring call, CSDE also stated that it had some districts that required additional support in the planning process and therefore, CSDE was providing additional technical assistance to these districts, consistent with the timelines of ESEA flexibility. |
| Next Steps | None. |

| Component 2.F | Provide incentives and supports to ensure continuous improvement in other Title I schools that, based on the SEA’s new AMOs and other measures, are not making progress in improving student achievement and narrowing achievement gaps beginning in the 2012–2013 school year. |
| --- | --- |
| Summary of Progress | During the exit conference, CSDE indicated that its other Title I schools are making use of the Connecticut Accountability for Learning Initiative (CALI), a statewide model of continuous school and district improvement, with the goal of closing Connecticut’s achievement gaps. CSDE’s approved ESEA flexibility request details that CALI provides ongoing professional development and technical assistance focused on a series of flexible training modules that cover topics including: instructional and school data teams, differentiated instruction, assessment, and climate. Also, CSDE indicated that during the 2012–2013 school year, it is implementing a district-wide initiative for reform as well as school-specific reforms and that it intends to work directly with its schools to develop school-specific plans. Consistent with its approved ESEA flexibility request, CSDE reported that it has created a category of Review Schools to provide additional support to a subset of its lowest performing schools. CSDE’s Review Schools include a subset of its: focus schools, Title I schools and non-Title I schools. CSDE further indicated that most of its Review Schools are in its Alliance Districts, CSDE’s lowest-performing 30 districts, which are eligible for increased funding and include all but three of CSDE’s focus schools. In the 2013–2014 and 2014–2015 school years, Alliance Districts will take the following actions in Review Schools: prioritize schools according to need and implement appropriate supports and interventions to improve student performance. CSDE also reported that staffs from its Review Schools participate in CSDE conferences and use AMOs to guide interventions. |
| Next Steps | None. |

| Component 2.G | Build SEA, LEA, and school capacity to improve student learning in all schools and, in particular, in low-performing schools and schools with the largest achievement gaps, including through: providing timely and comprehensive monitoring of, and technical assistance for, LEA implementation of interventions in priority and focus schools, holding LEAs accountable for improving school and student performance, particularly for turning around their priority schools, and ensure sufficient support for implementation of interventions in priority schools, focus schools, and other Title I schools identified under the SEA’s differentiated recognition, accountability, and support system (including through leveraging funds the LEA was previously required to reserve under ESEA section 1116(b)(10), SIG funds, and other Federal funds, as permitted along with State and local resources). |
| --- | --- |
| Summary of Progress | During its monitoring call, CSDE stated that it has technical assistance (TA) teams working with its districts’ data teams. CSDE further indicated that its SEA TA teams were tasked with monitoring its LEA TA teams, and collaborating with its LEA TA teams to implement its ESEA flexibility accountability system. Additionally, CSDE indicated that its TA teams were utilizing quarterly benchmark assessments to inform the team’s work. CSDE also indicated that by the end of the 2012–2013 school year, it will develop plans for years two and three of implementation based on progress toward targets in the first year of implementation. CSDE further explained that a three-tier monitoring process will be implemented and will include self-assessment, desk review, and on-site monitoring. CSDE reported that these monitoring protocols will be developed by the second semester of the 2012–2013 school year and will align with the requirements set forth in ESEA flexibility. CSDE indicated that it has identified 30 LEAs as Alliance Districts—the districts with the lowest district performance index scores throughout the state are eligible for additional funding and support. |
| Next Steps | None. |

### Fiscal

| Use of Funds | The SEA ensures that its LEAs use Title I funds consistent with the SEA’s approved ESEA flexibility request through Waivers 2, 3, 5, and 9 in the document titled ESEA Flexibility, and any unwaived Title I requirements. |
| --- | --- |
| Summary of Progress | During its monitoring call, CSDE indicated that it has provided guidance to its LEAs on the allowable use of Title I funds under ESEA flexibility during the Alliance District information session (June 11, 2012), a Superintendents’ meeting on CSDE’s new accountability system (July 23, 2012), a back-to-school Superintendents’ meeting (August 28, 2012), and multiple electronic communications from CSDE’s Title I Director to LEA Title I Directors. In these electronic communications, representatives of CSDE specifically informed CSDE’s LEA Title I Directors that LEAs are no longer required to reserve 20 percent of Title I funds for supplemental educational services or public school choice. Also in these electronic communications, representatives of CSDE informed CSDE’s LEA Title I Directors that LEA and school improvement 10 percent reservations for professional development are no longer required. Representatives of CSDE informed CSDE’s LEA Title I Directors that the percentage limitation on transferability of funds has been waived such that LEAs may now programmatically transfer up to 100 percent of their Title II funds for allowable activities under Title II, Part D,; Title IV,; and Title V or into Title I, Part A; however, funds may not be transferred from Title I. |
| Next Steps | None. |

| Rank Order | The SEA ensures that its LEAs with Title I-eligible high schools with graduation rates below 60 percent that are identified as priority schools correctly implement the waiver that allows them to serve these schools out-of- rank order. |
| --- | --- |
| Summary of Progress | During its monitoring call, CSDE indicated that it has not identified any Title I-eligible high schools with graduation rates below 60 percent as priority schools and, therefore, does not have any LEAs that are taking advantage of the waiver to serve these schools out -of-rank order based on poverty rate. |
| Next Steps | None. |