Schedule of Deliverables

| Task # | Activity | Due (weeks after award) |
| --- | --- | --- |
| 1.0 | Meet with ED | 1 |
| 1.0 | Memo summarizing meeting | 2 |
| 2.0 | Updated design, including updated framework | 3 |
| 2.0 | Draft instruments | 3 |
| 3.1 | List of proposed sites for pilot study | 3 |
| 3.2 | Begin to recruit sites for pilot study | 5 |
| 3.3 | Begin to conduct pilot study | 7 |
| 3.4 | Report on pilot study and revised instruments | 12 |
| 3.4 | Meet with ED | 13 |
| 3.4 | Memo summarizing meeting and revised schedule of deliverables | 14 |
| 4.1 | Draft OMB package | 16 |
| 4.2 | Revise OMB package | 21 |
| 4.2 | Respond to comments from reviewers | 21 through 41 |
| 5.1 | Draw survey sample | 26 |
| 5.1 | Begin contacting respondents | 29 |
| 5.2 | Begin to implement data collection plan | 42(1 week after clearance) |
| 5.3 | Begin to implement data analysis plan | 54 |
| 5.4 | First draft survey report | 64 |
| 5.4 | Revised draft of survey report | 69 |
| 5.4 | Final survey report | 74 |
| 6.1 | Begin to contact states for Governors’ grantees | 42(1 week after clearance) |
| 6.1 | Draw Governors’ study sample | 50 |
| 6.1 | Begin contacting respondents | 53 |
| 6.2 | Begin to implement data collection plan | 59 |
| 6.3 | Begin to implement data analysis plan | 71 |
| 6.4 | First draft Governors’ study report | 81 |
| 6.4 | Revised draft of Governor’s study report | 86 |
| 6.4 | Final Governors’ study report | 91 |
| 7.1 | Select case study sites | 75 |
| 7.1 | Begin contacting respondents | 80 |
| 7.2 | Begin to conduct first year of case studies | 110 |
| 7.3 | Begin to analyze first year case study data | 120 |
| 7.4 | First draft case study interim report | 130 |
| 7.4 | Revised draft of case study interim report | 135 |
| 7.4 | Final case study interim report | 140 |
| 7.2 | Begin to conduct second year of case studies | 160 |
| 7.3 | Begin to analyze second year case study data | 180 |
| 7.4 | First draft case study final report | 185 |
| 7.4 | Revised draft of case study final report | 190 |
| 7.4 | Final case study final report | 200 |
| 8.1 | Begin feasibility study data analysis | 69 |
| 8.2 | Select feasibility study subsample | 80 |
| 8.2 | Collect data (with first year case studies) | 110 |
| 8.3 | Conduct additional feasibility study data analysis | 120 |
| 8.4 | First draft feasibility study report | 144 |
| 8.4 | Revised draft of feasibility study report | 149 |
| 8.4 | Final feasibility study report | 154 |
| 9.1 | First draft of final summary report | 206 |
| 9.1 | Revised draft of final summary report | 211 |
| 9.1 | Final summary report | 216 |
| 9.2 | First draft of nontechnical report | 220 |
| 9.2 | Revised draft of nontechnical report | 225 |
| 9.2 | Final nontechnical report | 230 |
| 10.0 | Data and documentation | 236 |
|  | OPTIONAL TASK (Task 11) |  |
| 11.1 | Draft OMB package | 163 |
| 11.2 | Revised OMB package | 168 |
| 11.2 | Revised schedule of deliverables | 168 |
| 11.2 | Respond to comments from reviewers | 168 through 188 |
| 11.3 | Begin to select and contact respondents | 180 |
| 11.4 | Begin to collect data | 189(1 week after clearance) |
| 11.5 | Begin to analyze data | 205 |
| 11.6 | First draft of report | 221 |
| 11.6 | Revised draft of report | 226 |
| 11.6 | Final report | 231 |
| 11.7 | Data and documentation | 237 |
|  | Progress/Exception and labor/expenditure reports | Monthly |

These dates are estimates; actual dates will be determined by the final study design as approved by ED and cleared by OMB and by the revised schedule of deliverables prepared under Subtask 3.8 (and, for optional task 11, the revised schedule of deliverables prepared under Subtask 11.2) and approved by ED