# ESEA FLEXIBILITY PART A MONITORING REPORT FOR THE MICHIGAN DEPARTMENT OF EDUCATION

## Overview Of ESEA Flexibility Monitoring

The U.S. Department of Education (ED) is committed to supporting State educational agencies (SEAs) as they implement ambitious reform agendas through their approved ESEA flexibility requests.  Consistent with this commitment, ED has developed a monitoring process that is designed to both ensure that each SEA implements its plan fully, effectively, and in a manner that is consistent with its approved request and the requirements of ESEA flexibility, as well as support each SEA with technical assistance to help ensure its implementation increases the quality of instruction and improves student achievement for all students in the State and its local educational agencies (LEAs).  Through this process, ED aims to productively interact with SEAs and shift from a focus primarily on compliance to one focused on outcomes.

For the 2012–2013 school year, ED has divided its ESEA flexibility monitoring process into three components, which are designed to align with the real-time implementation occurring at the SEA, LEA, and school levels and be differentiated based on an SEA’s progress and depth of work:

- Part A provided ED with a deeper understanding of each SEA’s goals and approaches to implementing ESEA flexibility and ensured that each SEA had the critical elements of ESEA flexibility in place to begin implementation of its plan in the 2012–2013 school year.  Part A was conducted through desk monitoring.

- Parts B and C, which are under development, will include a broader look at an SEA’s implementation of ESEA flexibility across all three principles, including its transition to college- and career-ready standards, its process for developing and implementing teacher and principal evaluation and support systems, and follow-up monitoring on the implementation of interventions in priority and focus schools.  Parts B and C reviews also will include a closer examination of the use of annual measureable objectives (AMOs), graduation rate targets, and other measures to drive supports and incentives in other Title I schools.  In addition, Parts B and C monitoring will address select unwaived Title I requirements and any “next steps” identified in the ESEA Flexibility Part A Monitoring Report.  These reviews will be conducted through a combination of on-site monitoring, desk monitoring, and progress checks that will be differentiated based on an individual SEA’s circumstances and request.  The format of future reports may vary from Part A.

ED will support each SEA in its implementation of ESEA flexibility across all three monitoring components and will work with each SEA to identify areas for additional technical assistance.

This ESEA Flexibility Part A Monitoring Report provides feedback to the Michigan Department of Education (MDE) on its progress implementing the components of ESEA flexibility identified in the document titled ESEA Flexibility Part A Monitoring Protocol to ensure the SEA implements ESEA flexibility fully, effectively, and in a manner that is consistent with the SEA’s approved request and the requirements of ESEA flexibility.  This report is based on information provided through SEA-submitted documentation, a monitoring call conducted with MDE staff on October 24, 2012, and a follow-up exit conference call held on November 13, 2012.  Generally, this report does not reflect steps taken by the SEA after the exit conference.

The report consists of the following sections:

- Highlights of MDE’s Implementation of ESEA Flexibility.  This section identifies key accomplishments in the SEA’s implementation of ESEA flexibility as of the SEA’s monitoring call on October 24, 2012.

- Summary of MDE’s Implementation of ESEA Flexibility and Next Steps.  This section provides a snapshot of the SEA’s progress in implementing each component of ESEA flexibility or unwaived Title I requirement based on the evidence MDE described during its monitoring phone call on October 24, 2012, through written documentation provided to ED, and any further clarifications provided by the SEA during its exit conference phone call on November 13, 2012.  Where appropriate, this section also includes a set of “next steps” that were discussed with the SEA during its exit conference phone call, to ensure that the SEA implements the components of ESEA flexibility consistent with the principles and timelines in ESEA Flexibility and MDE’s approved request.

## Highlights Of MDE’s Implementation Of Esea Flexibility

- Based on information provided during the monitoring conference call and through written documentation, MDE’s work implementing ESEA flexibility includes the following key accomplishments:

  - Requiring LEAs with focus schools to conduct diagnostic dialogues with those schools that involve deep data dives and root cause analyses so that schools understand the reasons for their focus school identification and are able to plan interventions accordingly.

  - Building capacity in intermediate school districts so that they will be able to help coach low-performing schools.

## Summary Of MDE’s Progress Implementing ESEA Flexibility And Next Steps

### Principle 2: State-Developed Differentiated Recognition, Accountability, and Support

| Component 2.A | Develop and implement beginning in the 2012–2013 school year a system of differentiated recognition, accountability, and support for all LEAs in the State and for all Title I schools in these LEAs. |
| --- | --- |
| Summary of Progress | MDE indicated during the monitoring call that it ran its interim system of differentiated recognition, accountability, and support on June 20, 2012, based on AYP and their statewide Top-to-Bottom rankings to classify schools using 2011–2012 data. MDE explained that quality control processes identified a necessary coding change to the social studies test. MDE reported that it made the appropriate coding change and completed the extensive quality control process to ensure accuracy. |
| Next Steps | None. |

| Assurance 7 | Report to the public its lists of reward schools, priority schools, and focus schools at the time the SEA is approved to implement flexibility, and annually thereafter, it will publicly recognize its reward schools as well as make public its lists of priority and focus schools if it chooses to update those lists. |
| --- | --- |
| Summary of Progress | MDE publicly reported its lists of 146 priority schools, and 358 focus schools on August 1, 2012 by posting them on the SEA’s website at: http://www.mi.gov/mde/0,4615,7-140-22709---,00.html (valid as of December 20, 2012). MDE indicated that its list of reward schools, published on August 1, 2012, was incomplete because it did not include “Beating the Odds” schools. MDE reported that the complete list would be presented at a State Board of Education meeting on November 20, 2012. MDE stated that its complete list of reward schools would be made public at the end of Novemeber 2012. |
| Next Steps | To ensure that the SEA publicly reports its lists of reward schools consistent with the principles and timelines of ESEA Flexibility: The SEA will make public its list of 344 reward schools on November 20, 2012. ED confirmed that the SEA posted its list on this date. |

| Component 2.D | Effect dramatic, systemic change in the lowest-performing schools by publicly identifying priority schools and ensuring that each LEA with one or more of these schools implements, for three years, meaningful interventions aligned with the turnaround principles in each of these schools beginning no later than the 2014–2015 school year. |
| --- | --- |
| Summary of Progress | MDE indicated that it has identified 146 priority schools, all of which will implement interventions in the 20122013 school year. Nineteen of these priority schools are schools receiving School Improvement Grant (SIG) funds. According to MDE, all of these priority schools intend to implement one of the four SIG models beginning January 1, 2013. MDE indicated that it is currently developing intervention plans for newly awarded SIG schools and that other schools are in their second or third year of implementation. MDE noted that a SIG school that was also in the lowest 5 percent was identified as a priority school, and a SIG school not identified as a priority school will continue to implement its SIG plan. MDE indicated that according to State law, non-SIG priority schools have one year of planning and must start implementation by September 2014. However, MDE noted that many of these schools start implementation as soon as their plan is approved. MDE indicated that it has been replacing principals in priority schools, but that there is also a strong focus on providing the necessary supports to leaders to develop capacity so that leadership responsibilities are distributed across a wider group rather than just the principal. MDE assigned an intervention specialist to each priority school to conduct diagnostic dialogues to facilitate plan development. |
| Next Steps | None. |

| Component 2.E | Work to close achievement gaps by publicly identifying Title I schools with the greatest achievement gaps, or in which subgroups are furthest behind, as focus schools and ensuring that each LEA implements interventions, which may include tutoring or public school choice, in each of these schools based on reviews of the specific academic needs of the school and its students beginning in the 2012–2013 school year. |
| --- | --- |
| Summary of Progress | In preparation for implementing interventions in the first semester, MDE indicated that it asked all LEAs with focus schools to conduct “diagnostic dialogues” with their schools. These dialogues serve as needs assessments involving deep data dives and root-cause analyses to diagonose issues and develop meaningful solutions. MDE indicated that schools must submit one or two teaching and learning priorities developed as a result of the dialogues by December 2012. MDE stated that Michigan State University-trained facilitators are helping Title I focus schools conduct their diagnostic dialogues. MDE provides a district toolkit for all LEAs with focus schools that includes examples of interventions and strategies. MDE indicated that the toolkit will be posted on the SEA’s website. MDE partnered with Education Resource Strategies to provide a “Resource Check” tool which will serve as a LEA-level self assessment. Additionally, MDE’s focus school monitoring will evaluate LEAs’ Resource Check self-assessments and their LEA-level benchmarks for Title I. |
| Next Steps | None. |

| Component 2.F | Provide incentives and supports to ensure continuous improvement in other Title I schools that, based on the SEA’s new AMOs and other measures, are not making progress in improving student achievement and narrowing achievement gaps beginning in the 2012–2013 school year. |
| --- | --- |
| Summary of Progress | MDE indicated that LEA and school plans for incentives and supports in other Title I schools are submitted through its consolidated application process. MDE further explained that it reviews the plans for individual schools and LEAs that are not making AYP to ensure their plans address the issues identified in their comprehensive needs assessment and that supplementary resources are aligned to address those needs. MDE expressed that although the process is lengthy, it expected schools to update their plans during the first semester of the 2012–2013 school year. MDE noted that updated plans will then be loaded into MDE’s school improvement templates and the reviewing and monitoring process will begin. MDE reported that it will begin on-site monitoring of approximately 100 districts in December 2012 or January 2013. |
| Next Steps | None. |

| Component 2.G | Build SEA, LEA, and school capacity to improve student learning in all schools and, in particular, in low-performing schools and schools with the largest achievement gaps, including through: providing timely and comprehensive monitoring of, and technical assistance for, LEA implementation of interventions in priority and focus schools; holding LEAs accountable for improving school and student performance, particularly for turning around their priority schools; and ensuring sufficient support for implementation of interventions in priority schools, focus schools, and other Title I schools identified under the SEA’s differentiated recognition, accountability, and support system (including through leveraging funds the LEA was previously required to reserve under ESEA section 1116(b)(10), SIG funds, and other Federal funds, as permitted, along with State and local resources.) |
| --- | --- |
| Summary of Progress | MDE indicated that its plan for monitoring non-SIG priority schools includes quarterly site visits and monthly phone calls. Schools will also have to provide information electronically. This information is mainly collected at the school level, but MDE is also gathering some LEA-level information. MDE indicated that monitoring continues on a weekly basis in schools that are struggling or otherwise in need of assistance but indicated that it brings schools and LEAs in for discussions if any issues arise. MDE is currently working closely with two LEAs to address concerns. MDE further indicated that it monitors its focus schools at the LEA-level. MDE noted that it will customize professional learning to address any issues that are identified through monitoring. MDE is working to ensure that all schools understand what is taking place by providing the School Reform Office as a resource. MDE noted that it will be looking at the new assessment results data to determine at the LEA level if students are meeting college and career ready standards. |
| Next Steps | None. |

### Fiscal

| Use of Funds | The SEA ensures that its LEAs use Title I funds consistent with the SEA’s approved ESEA flexibility request under Waivers 2, 3, 5, and 9 in the document titled ESEA Flexibility, and any unwaived Title I requirements. |
| --- | --- |
| Summary of Progress | MDE indicated that it provided guidance regarding the set-aside of Federal funds through three PowerPoints presented at meetings in September 2012 with district coordinators and administrators. In addition, MDE noted that it issued an FAQ document about choice and transportation requirements on Sepetember 7, 2012. |
| Next Steps | None. |

| Rank Order | The SEA ensures that LEAs with Title I eligible high schools with graduation rates below 60 percent that are identified as priority schools correctly implement the waiver that allows them to serve these schools out-of-rank order. |
| --- | --- |
| Summary of Progress | MDE has not identified any Title I-eligible high schools with graduation rates below 60 percent as priority schools and, therefore, does not have any LEAs that are taking advantage of the waiver to serve these schools out of rank order based on poverty rate. |
| Next Steps | None. |