# ESEA FLEXIBILITY PART A MONITORING REPORT FOR THE NEW JERSEY DEPARTMENT OF EDUCATION

## Overview Of ESEA Flexibility Monitoring

The U.S. Department of Education (ED) is committed to supporting State educational agencies (SEAs) as they implement ambitious reform agendas through their approved ESEA flexibility requests.  Consistent with this commitment, ED has developed a monitoring process that is designed to both ensure that each SEA implements its plan fully, effectively, and in a manner that is consistent with its approved request and the requirements of ESEA flexibility, as well as support each SEA with technical assistance to help ensure its implementation increases the quality of instruction and improves student achievement for all students in the State and its local educational agencies (LEAs).  Through this process, ED aims to productively interact with SEAs and shift from a focus primarily on compliance to one focused on outcomes.

For the 2012–2013 school year, ED has divided its ESEA flexibility monitoring process into three components, which are designed to align with the real-time implementation occurring at the SEA, LEA, and school levels and be differentiated based on an SEA’s progress and depth of work:

- Part A provided ED with a deeper understanding of each SEA’s goals and approaches to implementing ESEA flexibility and ensured that each SEA had the critical elements of ESEA flexibility in place to begin implementation of its plan in the 2012–2013 school year.  Part A was conducted through desk monitoring.

- Parts B and C, which are under development, will include a broader look at an SEA’s implementation of ESEA flexibility across all three principles, including its transition to college- and career-ready standards, its process for developing and implementing teacher and principal evaluation and support systems, and follow-up monitoring on the implementation of interventions in priority and focus schools.  Parts B and C reviews also will include a closer examination of the use of annual measureable objectives (AMOs), graduation rate targets, and other measures to drive supports and incentives in other Title I schools.  In addition, Parts B and C monitoring will address select unwaived Title I requirements and any “next steps” identified in the ESEA Flexibility Part A Monitoring Report.  These reviews will be conducted through a combination of on-site monitoring, desk monitoring, and progress checks that will be differentiated based on an individual SEA’s circumstances and request.  The format of future reports may vary from Part A.

ED will support each SEA in its implementation of ESEA flexibility across all three monitoring components and will work with each SEA to identify areas for additional technical assistance.

This ESEA Flexibility Part A Monitoring Report provides feedback to the New Jersey Department of Education (NJDOE) on its progress implementing the components of ESEA flexibility identified in the document titled ESEA Flexibility Part A Monitoring Protocol to ensure the SEA implements ESEA flexibility fully, effectively, and in a manner that is consistent with the SEA’s approved request and the requirements of ESEA flexibility.  This report is based on information provided through SEA-submitted documentation, a monitoring call conducted with NJDOE staff on October 10, 2012, and a follow-up exit conference call held on January 23, 2013.  Generally, this report does not reflect steps taken by the SEA after the exit conference.

The report consists of the following sections:

- Highlights of NJDOE’s Implementation of ESEA Flexibility.  This section identifies key accomplishments in the SEA’s implementation of ESEA flexibility as of the SEA’s monitoring call on October 10, 2012.

- Summary of NJDOE’s Implementation of ESEA Flexibility and Next Steps.  This section provides a snapshot of the SEA’s progress implementing each component of ESEA flexibility or unwaived Title I requirement based on the evidence NJDOE described during its monitoring phone call on October 10, 2012, through written documentation provided to ED, and any further clarifications provided by the SEA during its exit conference phone call on January 23, 2013.  Where appropriate, this section also includes a set of “next steps” that were discussed with the SEA during its exit conference phone call, to ensure that the SEA implements the components of ESEA flexibility consistent with the principles and timelines in ESEA Flexibility and NJDOE’s approved request.

## Highlights Of NJDOE’s Implementation Of Esea Flexibility

Based on information provided during the monitoring conference call and through written documentation, NJDOE’s work implementing ESEA flexibility includes the following key accomplishments:

  - Focus and priority schools being held accountable for improvements directly by the SEA, through its seven new Regional Achievement Centers (RACs) which work with these schools to identify needed improvements (Quality School Reviews), develop School Improvement Plans (SIPs) and successfully implement aligned interventions.

  - Piloting of its teacher evaluation system in 11 LEAs, including 19 School Improvement Grant (SIG) schools, in 2011–2012 and in 25–30 LEAs in 2012–2013.

## Summary Of NJDOE’S Progress Implementing ESEA Flexibility And Next Steps

### Principle 2: State-Developed Differentiated Recognition, Accountability, and Support

| Component 2.A | Develop and implement beginning in the 2012–2013 school year a system of differentiated recognition, accountability, and support for all LEAs in the State and for all Title I schools in these LEAs. |
| --- | --- |
| Summary of Progress | NJDOE indicated that it ran its system of differentiated recognition, accountability, and support, which compares school performance against performance targets in four areas (academic achievement, college/career readiness, graduation/post-secondary, closing achievement gaps) and was on track to issue performance reports in February 2013. NJDOE indicated that it generated a preliminary list of priority and focus schools based on 2011–2012 data in April 2012. The SEA encountered the following issues upon running its new system: determination of the status of schools with reconfigured grade levels; quality of graduation rate data for one high school; and definition of what constitutes a “school building.” Upon resolution of these issues, the SEA forwarded its final lists of priority and focus schools to ED on October 12, 2012. NJDOE indicated during the exit conference call that it had not yet identified its reward schools based on 2011–2012 data because it is still conducting the appeals process for determining whether or not schools met all proficiency AMOs, which is one factor for determining reward school status. |
| Next Steps | NJDOE will publicly report its list of reward, priority and focus schools consistent with the principles and timelines of ESEA Flexibility. ED confirmed that on January 31, 2013, NJDOE posted its final list of priority and focus schools at: http://www.nj.gov/education/reform/PFRschools/PriorityFocusSchools.pdf (valid as of April 26, 2013) and on March 1, 2013, NJDOE posted its final list of 57 rewards schools at: http://www.nj.gov/education/reform/PFRschools/RewardSchools.pdf (valid as of April 26, 2013). |

| Assurance 7 | Report to the public its lists of reward schools, priority schools, and focus schools at the time the SEA is approved to implement flexibility. Annually thereafter, it will publicly recognize its reward schools, as well as make public its lists of priority and focus schools if it chooses to update those lists. |
| --- | --- |
| Summary of Progress | During the exit conference call, NJDOE indicated it had not publicly posted its final lists of reward, priority and focus schools because it was planning to do so when reward schools are finalized; however it has forwarded to ED the final schools lists of 182 focus schools (145 Title I schools) and 75 priority schools (73 Title I schools). |
| Next Steps | NJDOE will publicly reports its list of reward, priority and focus schools consistent with the principles and timelines of ESEA Flexibility. ED confirmed that on January 31, 2013, NJDOE posted its final list of priority and focus schools at: http://www.nj.gov/education/reform/PFRschools/PriorityFocusSchools.pdf and on March 1, 2013, NJDOE posted its final list of 57 rewards schools at: http://www.nj.gov/education/reform/PFRschools/RewardSchools.pdf. |

| Component 2.D | Effect dramatic, systemic change in the lowest-performing schools by publicly identifying priority schools and ensuring that each LEA with one or more of these schools implements, for three years, meaningful interventions aligned with the turnaround principles in each of these schools beginning no later than the 2014–2015 school year. |
| --- | --- |
| Summary of Progress | NJDOE indicated during the monitoring phone call that for the 2012–2013 school year, all 75 of NJDOE’s priority schools will implement interventions. Nineteen of these priority schools are schools receiving School Improvement Grant (SIG) funds to implement one of four SIG models. NJDOE indicated that it intends for all 56 non-SIG priority schools to implement interventions aligned with the seven ESEA flexibility turnaround principles; however, only four principles would be emphasized in 2012–2013 school year interventions, while the remaining principles would be more comprehensively addressed in the 2013–2014 school year, per its approved request. During the exit conference call, NJDOE indicated that it had not reviewed the extent to which priority schools were addressing all seven ESEA flexibility turnaround principles concurrently in the 20122013 school year, including how some principles might be emphasized in school improvement plans more than others. Subsequent to the monitoring phone call, ED verified that 19 schools are currently implementing a SIG model. Two additional SIG grants in Cohort I were not renewed. Network Turnaround Officers who served SIG schools are in the process of being replaced with State Turnaround Coaches (STCs) who will serve both SIG and non-SIG priority schools. The STCs provide both monitoring and support to schools as part of the RACs. To ensure strong leadership in schools, NJDOE required the replacement of all principals in priority schools who have been in place for three or more years, at the beginning of the 2012–2013 school year. NJDOE received six appeals and granted one waiver. NJDOE indicated that to ensure effective instruction, Quality School Reviews are required to identify areas of instructional weakness and that this would be a focus area of RACs, including the deployment of appropriate professional development and the use of rubrics for teacher evaluation. Additionally, RACs will utilize turnaround coaches to train principals to ensure that effective instruction is taking place. NJDOE indicated during the monitoring phone call that each priority school has been notified of its status, completed a QSR in collaboration with its respective RAC, and is on-track to submit school improvement plans, created with RAC assistance, to the central SEA office by October 29, 2012. During the exit conference call, NJDOE indicated that by mid-November, RACs had reviewed most school improvement plans and that only a small number of school improvement plans for priority schools were still under development. NJDOE indicated during the exit conference that all priority schools would be fully implementing between January–June 2013. |
| Summary of Progress (cont’d) | NJDOE indicated during the monitoring phone call that RACs will evaluate the progress of schools towards successful implementation on a 7-week cycle. The SEA is developing the School Accountability Management System (SAMS) to leverage both student performance data and school milestone data to execute needs assessments and track school progress towards meeting these objectives. The system is tightly aligned with NJDOE’s turnaround principles. During the exit conference call, however, NJDOE indicated that it had encountered difficulties deploying the implementation-tracking component of SAMS that ensures alignment of school-level interventions with the turnaround principles and that it is now planning on using an alternative software platform, already in use at NJDOE, for this function, to be launched in February, 2013. NJDOE indicated in a follow-up discussion after the monitoring phone call that its RACs would not be utilized for improvement activities in its five charter priority schools, due in large part to legal restrictions preventing overly- proscriptive measures by the SEA in charter schools, and that it would determine and implement alternative procedures to comply with ESEA flexibility requirements regarding implementation in priority schools for charter schools. |
| Next Steps | In order to ensure that implementation of meaningful interventions aligned with all the turnaround principles takes place in all priority schools for at least three years, ED will revisit, during Part B monitoring, the status of implementation in non-SIG priority schools and will review evidence and timelines related to this implementation. |

| Component 2.E | Work to close achievement gaps by publicly identifying Title I schools with the greatest achievement gaps, or in which subgroups are furthest behind, as focus schools and ensuring that each LEA implements interventions. This may include tutoring or public school choice, in each of these schools based on reviews of the specific academic needs of the school and its students beginning in the 2012-2013 school year. |
| --- | --- |
| Summary of Progress | NJDOE indicated during the monitoring phone call that its focus schools are required to complete the QSR as a self-assessment (rather than as a RAC-led onsite review like that conducted for priority schools), submit school improvement plans aligned with the QSR by October 29, 2012 to their respective RACs, and begin interventions aligned to reasons for identification by November 1, 2012. NJDOE indicated during the monitoring phone call that each RAC is currently working with all of its identified focus schools, to help finalize SIPs (initial drafting of school improvement plans is done at the school-level, not collaboratively). The RAC’s role in QSR development in focus schools is quality assurance and approval of conclusions. During the exit conference call, NJDOE indicated that by mid-November, RACs had reviewed most school improvement plans and that only a small number of focus school plans were still under development. The SEA also indicated that all focus schools, except those with outstanding school improvement plans, had begun interventions during the first semester of the 2012–2013 school year. NJDOE indicated that its RACs will utilize SAMS and meetings with schools to ensure fidelity of implementation on a 7-week cycle, over the course of a minimum 2-year implementation. Monitoring processes for focus and priority schools are the same. During the exit conference call, NJDOE indicated that a replacement system for SAMS would be deployed in February 2013 (per above). |
| Next Steps | In order to ensure that implementation of interventions based on reviews of the specific academic needs of the school and its students takes place in all focus schools, ED will revisit, during Part B monitoring, the status of implementation in these schools and will review evidence and timelines related to this implementation. |

| Component 2.F | Provide incentives and supports to ensure continuous improvement in other Title I schools that, based on the SEA’s new AMOs and other measures, are not making progress in improving student achievement and narrowing achievement gaps beginning in the 2012–2013 school year. |
| --- | --- |
| Summary of Progress | NJDOE indicated and provided evidence that all non-priority and non-focus Title I schools that missed a single math or reading proficiency AMO for the 2011–2012 school year received a letter the week of October 9, 2012 that: details all AMOs met or missed indicates that schools have until November 9, 2012 to appeal the AMO achievement data provided by the SEA encourages schools to begin developing appropriate improvement strategies during this appeal period, including alignment of Title I funds to address needs of subgroups that missed targets indicates that LEAs of these schools will be contacted to initiate development of school improvement plans to support identified subgroups. NJDOE provided evidence of additional guidance it distributed to LEAs that non-priority and non-focus Title I schools with low performance against proficiency AMOs must submit Progress Targets Action Plans by November 30, 2012 and implement targeted interventions between January and June, 2013. The guidance indicated the SEA will notify the public of the names of schools that missed AMOs by December 14, 2012. During the exit conference call, the SEA indicated that monitoring for implementation in these schools and proper use of Title I funds will occur within the context of the Title I consolidated monitoring process. During the exit conference call, NJDOE also indicated that it had not completed the appeals process and did not provide a projected finish date. NJDOE indicated during the monitoring phone call that it had not used subgroup performance against graduation rate targets as criteria for identification of other Title I schools needing additional support. However, NJDOE indicated during the exit conference call that schools that are identified based on missed proficiency AMOs are required to develop a Progress Targets Action Plan that articulates how the school will address the needs of student populations that did not meet graduation rate targets. NJDOE indicated that in the 2012–2013 and 2013–2014 school years, RACs will be working with priority and focus schools, not Title I schools identified for missed proficiency AMOs. NJDOE has posted various technical assistance documents to its website for all schools to use, however, including QSR and SIP templates and program target plans. Additionally, the Commissioner sends out a weekly email promoting various available resources. NJDOE will also, beginning after the 2013–2014 school year, identify and provide additional supports to the bottom five percent of Title I schools (that are not already identified as priority schools) that miss a reading or math AMO two years in a row, based on 2012–2013 and 2013–2014 assessment data. |
| Next Steps | To ensure that incentives and supports are provided to other Title I schools, based on performance against the SEA’s new AMOs and other measures, the SEA will submit an amendment to its ESEA flexibility request describing how it will use graduation rate data to drive interventions in other Title I schools. |

| Component 2.G | Build SEA, LEA, and school capacity to improve student learning in all schools and, in particular, in low-performing schools and schools with the largest achievement gaps, including through: providing timely and comprehensive monitoring of, and technical assistance for, LEA implementation of interventions in priority and focus schools, holding LEAs accountable for improving school and student performance, particularly for turning around their priority schools, and ensure sufficient support for implementation of interventions in priority schools, focus schools, and other Title I schools identified under the SEA’s differentiated recognition, accountability, and support system (including through leveraging funds the LEA was previously required to reserve under ESEA section 1116(b)(10), SIG funds, and other Federal funds, as permitted along with State and local resources). |
| --- | --- |
| Summary of Progress | NJDOE reiterated on the monitoring phone call that RACs, not LEAs, are the main accountability unit for school performance within its new accountability system; however, the feedback from RACs as of the exit conference is that they are collaborating to a significant extent directly with LEAs. NJDOE indicated that LEAs are accountable for other school-level capacity indicators through its Title I consolidated monitoring process and for compliance with operational, fiscal management, governance and personnel requirements through its Quality Single Accountability Continuum process, driven by the SEA’s county offices. NJDOE also provided evidence that LEAs are required to and are on-track to develop Progress Targets Action Plans addressing reasons for low performance against proficiency AMOs in other Title I schools, holding public meetings about the plans, and having them approved by school boards. LEAs must upload finalized SIPs to websites and notify county offices when complete. NJDOE indicated in the exit conference call that RACs are approximately 80 percent staffed, including experts to address issues regarding English learners and students with disabilities (76 of 80 projected staff members hired). |
| Next Steps | None. |

### Fiscal

| Use of Funds | The SEA ensures that its LEAs use Title I funds consistent with the SEA’s approved ESEA flexibility request, through Waivers 2, 3, 5, and 9 in the document titled ESEA Flexibility, and any unwaived Title I requirements. |
| --- | --- |
| Summary of Progress | NJDOE indicated that it is requiring LEAs to set-aside 30 percent of Title I, Part funds to support interventions in focus and priority schools, and that it issued guidance to LEAs in July, 2012 regarding this. NJDOE also indicated that is has provided a revised consolidated application for LEAs that addresses use of funds under ESEA flexibility. |
| Next Steps | None. |

| Rank Order | The SEA ensures that its LEAs with Title I eligible high schools with graduation rates below 60 percent that are identified as priority schools correctly implement the waiver that allows them to serve these schools out-of-rank order. |
| --- | --- |
| Summary of Progress | NJDOE indicated during the monitoring phone call that none of its districts are utilizing this waiver. |
| Next Steps | None. |