# ESEA FLEXIBILITY PART A MONITORING REPORT FOR THE

# OREGON DEPARTMENT OF EDUCATION

## Overview Of ESEA Flexibility Monitoring

The U.S. Department of Education (ED) is committed to supporting State educational agencies (SEAs) as they implement ambitious reform agendas through their approved ESEA flexibility requests.  Consistent with this commitment, ED has developed a monitoring process that is designed to both ensure that each SEA implements its plan fully, effectively, and in a manner that is consistent with its approved request and the requirements of ESEA flexibility, as well as support each SEA with technical assistance to help ensure its implementation increases the quality of instruction and improves student achievement for all students in the State and its local educational agencies (LEAs).  Through this process, ED aims to productively interact with SEAs and shift from a focus primarily on compliance to one focused on outcomes.

For the 2012–2013 school year, ED has divided its ESEA flexibility monitoring process into three components, which are designed to align with the real-time implementation occurring at the SEA, LEA, and school levels and be differentiated based on an SEA’s progress and depth of work:

- Part A provided ED with a deeper understanding of each SEA’s goals and approaches to implementing ESEA flexibility and ensured that each SEA had the critical elements of ESEA flexibility in place to begin implementation of its plan in the 2012–2013 school year.  Part A was conducted through desk monitoring.

- Parts B and C, which are under development, will include a broader look at an SEA’s implementation of ESEA flexibility across all three principles, including its transition to college- and career-ready standards, its process for developing and implementing teacher and principal evaluation and support systems, and follow-up monitoring on the implementation of interventions in priority and focus schools.  Parts B and C reviews also will include a closer examination of the use of annual measureable objectives (AMOs), graduation rate targets, and other measures to drive supports and incentives in other Title I schools.  In addition, Parts B and C monitoring will address select unwaived Title I requirements and any “next steps” identified in the ESEA Flexibility Part A Monitoring Report.  These reviews will be conducted through a combination of onsite monitoring, desk monitoring, and progress checks that will be differentiated based on an individual SEA’s circumstances and request.  The format of future reports may vary from Part A.

ED will support each SEA in its implementation of ESEA flexibility across all three monitoring components and will work with each SEA to identify areas for additional technical assistance.

This ESEA Flexibility Part A Monitoring Report provides feedback to the Oregon Department of Education (ODE) on its progress in implementing the components of ESEA flexibility identified in the document titled ESEA Flexibility Part A Monitoring Protocol to ensure the SEA implements ESEA flexibility fully, effectively, and in a manner that is consistent with the SEA’s approved request and the requirements of ESEA flexibility.  This report is based on information provided through SEA-submitted documentation, a monitoring call conducted with ODE staff on September 18, 2012, and a follow-up exit conference phone call held on October 1, 2012.  Generally, this report does not reflect steps taken by the SEA after the exit conference.

The report consists of the following sections:

- Highlights of ODE’s Implementation of ESEA Flexibility.  This section identifies key accomplishments in the SEA’s implementation of ESEA flexibility as of the SEA’s monitoring call on September 18, 2012.

- Summary of ODE’s Implementation of ESEA Flexibility and Next Steps.  This section provides a snapshot of the SEA’s progress in implementing each component of ESEA flexibility or unwaived Title I requirement based on the evidence ODE described during its monitoring phone call on September 18, 2012, through written documentation provided to ED, and any further clarifications provided by the SEA during its exit conference phone call on October 1, 2012.  Where appropriate, this section also includes a set of “next steps” that were discussed with the SEA during its exit conference phone call, to ensure that the SEA implements the components of ESEA flexibility consistent with the principles and timelines in ESEA Flexibility and the ODE’s approved request.

## Highlights Of ODE’s Implementation Of Esea Flexibility

- Based on the information provided during the monitoring conference phone call and through written documentation, ODE’s work implementing ESEA flexibility includes the following key accomplishments:

  - Supporting principals in all priority and focus schools through assignment of Leadership Coaches to each identified school.

  - Implementing an online needs assessment and planning tool to support improvement planning in priority, focus, and other Title I schools.

## Summary Of ODE’s Progress Implementing ESEA Flexibility And Next Steps

### Principle 2: State-Developed Differentiated Recognition, Accountability, and Support

| Component 2.A | Develop and implement beginning in the 2012–2013 school year a system of differentiated recognition, accountability, and support for all LEAs in the State and for all Title I schools in these LEAs. |
| --- | --- |
| Summary of Progress | ODE indicated during the monitoring call that it is in process of running its system of differentiated recognition, accountability, and support based on 2011–2012 data to issue Oregon’s interim Report Cards. At the time of the call, ODE was scheduled to provide LEAs with a preliminary look at the ratings that schools would receive (i.e., “outstanding”, “satisfactory”, or “in need of improvement”) on September 20, 2012. ODE will release the final Oregon interim Report Card to LEAs and the media on October 4, 2012 and to the public on October 11, 2012. ED confirmed that subsequent to the call ODE released the LEA and school report cards on October 11, 2012. |
| Next Steps | None. |

| Assurance 7 | Report to the public its lists of reward schools, priority schools, and focus schools at the time the SEA is approved to implement flexibility, and annually thereafter, it will publicly recognize its reward schools as well as make public its lists of priority and focus schools if it chooses to update those lists. |
| --- | --- |
| Summary of Progress | On July 20, 2012, ODE sent an email notification to all LEAs with identified priority or focus schools and the Chief Education Officer (CEdO) personally followed up this notification with a phone call to the administration of each identified LEA. ODE publicly reported its preliminary list of 27 Model (reward) schools, 37 priority schools, and 60 focus schools on August 3, 2012. There were two changes in the list of priority and focus schools once small school rules were applied with the list posted on its website at: http://www.ode.state.or.us/wma/superintendent/release/final-priority-focus-and-model-schools-list.pdf (valid as of February 7, 2013). ODE began conducting workshops and providing supports to priority and focus schools once its preliminary list was made public. |
| Next Steps | None. |

| Component 2.D | Effect dramatic, systemic change in the lowest-performing schools by publicly identifying priority schools and ensuring that each LEA with one or more of these schools implements, for three years, meaningful interventions aligned with the turnaround principles in each of these schools beginning no later than the 2014–2015 school year. |
| --- | --- |
| Summary of Progress | According to ODE, of the 37 priority schools that have been identified, 17 are receiving School Improvement Grant (SIG) funds and will continue implementation of their selected SIG models. The remaining 20 priority schools will use the 2012–2013 school year as a planning year with full implementation to begin in the 2013–2014 school year. On August 13 and 16, 2012, the ODE conducted “Unwrapping School Improvement” workshops with representatives from all priority schools in attendance. The conference provided information on the expectations for planning and implementation, as well as the supports available for priority schools, including the leadership coaches, use of the online Customized Planning Process Tool, School Appraisal Teams, the Continuous Improvement Network, School Support teams, and Regional Network Coordinators (RNC). The ODE indicated that leadership coaches have been assigned to all priority schools and are working with the principals in conducting their self-evaluations using Indistar, which the State identifies as their Customized Planning Process Tool (CPPT), an online tool for school reform planning and implementation. Moving forward, leadership coaches will work with schools on the development of their Comprehensive Achievement Plan (CAP). In order to facilitate the development of the school improvement plans, help focus their alignment on the issues leading to the school’s identification, ensure the plans are aligned with the turnaround principles, and assist in monitoring plan implementation, the SEA has required all plans be developed through the CPPT. The ODE also indicated School Appraisal Teams (SATs) will conduct in-depth onsite reviews of each newly identified priority school in October with final reports due in November, upon receipt of which schools will begin a four month planning process to address the findings of the SAT and determine the CAP elements for school reforms to be implemented in the 2013–2014 school year. Throughout this process RNCs will work with the leadership coaches within an assigned region to connect coaches and schools with additional resources, provide support and coordination to School Appraisal Teams and to School Support Teams, and support the SEA in oversight and monitoring of district CAPs and evaluating the quality of implementation. |
| Next Steps | To ensure that the SEA implements meaningful interventions in its SIG-awarded Tier I and/or Tier II schools consistent with the SIG final requirements and, therefore, may continue to count such schools as priority schools, consistent with the principles and timelines in ESEA Flexibility: ODE will work with ED’s Office of School Turnaround to resolve any outstanding monitoring findings relating to the implementation of the SIG models. |

| Component 2.E | Work to close achievement gaps by publicly identifying Title I schools with the greatest achievement gaps, or in which subgroups are furthest behind, as focus schools and ensuring that each LEA implements interventions, which may include tutoring or public school choice, in each of these schools based on reviews of the specific academic needs of the school and its students beginning in the 2012–2013 school year. |
| --- | --- |
| Summary of Progress | On August 13 and 16, 2012, the ODE conducted “Unwrapping School Improvement” workshops with representatives from all focus schools in attendance. The conference provided information on the expectations for planning and implementation, as well as the supports available for focus schools, including the leadership coaches, use of the online Customized Planning Process Tool, School Appraisal Teams, the Continuous Improvement Network, School Support teams, and Regional Network Coordinators. According to the ODE, leadership coaches are currently working with the principals in all focus schools to assist them in completing their self-evaluation. The self-evaluations are to be completed by September 30th each year, utilizing the State’s online CPPT. Because the self-evaluations are to be completed in the online CPPT, the SEA is continually monitoring the school planning progress and has been in touch with schools that are not making sufficient progress in completing their plans. Moving forward, ODE explained that leadership coaches will work with focus schools to develop their CAPs to ensure that they include interventions aligned with the reason for identification, which are to be submitted for ODE review by November 1st. The ODE will review and approve CAPs between November 13-16, 2012 to ensure that focus schools will implement interventions aligned with the reason for identification. ODE indicated that LEAs are to begin full implementation in all focus schools in December. Because ODE has mandated that the LEAs utilize the online CPPT in developing and implementing their CAPs, the SEA is able to monitor implementation by evaluating the congruence between the CAP’s implementation steps and school expenditures. SATs will conduct in depth reviews of all focus schools in December. The report produced by the SAT will be used by the school to inform revisions to the school’s CAP for implementation of interventions in the 2013–2014 school year. The Regional Network Coordinators will also work with the leadership coaches in focus schools to provide the same coordination, support, and monitoring they provide to priority schools. The School Support Teams will assist ODE in oversight and monitoring of district CAPs and evaluating the quality of implementation, as well as facilitate and support district participation in the Continuous Improvement Network (network). |
| Next Steps | None. |

| Component 2.F | Provide incentives and supports to ensure continuous improvement in other Title I schools that, based on the SEA’s new AMOs and other measures, are not making progress in improving student achievement and narrowing achievement gaps beginning in the 2012–2013 school year. |
| --- | --- |
| Summary of Progress | ODE explained that for the 2012–2013 school year it will identify other Title I schools that receive a rating of “In Needs of Improvement,” fail to meet participation rate for subgroups in mathematics and reading, and failed for two or more years to make progress in improving achievement of subgroups against AMOs by October 13, 2012. These schools will be required to develop a CAP that addresses the reason for identification, which the LEA is responsible for ensuring is implemented. The SEA indicated it still intends to identify a subset of these other Title I schools for State-directed support, but it would take additional time. Once those schools are identified, RNCs will be assigned by the SEA to work with the schools to conduct a self-evaluation and develop a CAP that addresses the reason for identification, which the LEA is responsible for ensuring is implemented. The RNC will also ensure that LEAs can contract for additional supports for their schools from the the network. ODE indicated that the LEAs understand they will need to provide incentives and supports to improve instruction in the other Title I schools identified. ODE indicated that the SEA will be able to use information from Indistar as well as from the Regional Network Coordinators to ensure incentives and supports are provided to the identified schools and targeted towards the specific reasons for identification and monitor implementation of the CAP. |
| Next Steps | None. |

| Component 2.G | Build SEA, LEA, and school capacity to improve student learning in all schools and, in particular, in low-performing schools and schools with the largest achievement gaps, including through: providing timely and comprehensive monitoring of, and technical assistance for, LEA implementation of interventions in priority and focus schools holding LEAs accountable for improving school and student performance, particularly for turning around their priority schools ensuring sufficient support for implementation of interventions in priority schools, focus schools, and other Title I schools identified under the SEA’s differentiated recognition, accountability, and support system (including through leveraging funds the LEA was previously required to reserve under ESEA section 1116(b)(10), SIG funds, and other Federal funds, as permitted, along with State and local resources). |
| --- | --- |
| Summary of Progress | ODE indicated that all LEAs and schools are being provided training on the CPPT online needs assessment and planning tool, and all LEAs are required to submit a revised district CAP, which is due no later than June 30, 2013. All LEAs will be assigned an RNC and will be provided access to the State’s Continuous Improvement Network. |
| Next Steps | None. |

### Fiscal

| Use of Funds | The SEA ensures that its LEAs use Title I funds consistent with the SEA’s approved ESEA flexibility request through Waivers 2, 3, 5, and 9 in the document titled ESEA Flexibility, and any unwaived Title I requirements. |
| --- | --- |
| Summary of Progress | During its “Odyssey Conference”, which was held on August 14 and 15, 2012 for all LEAs in the State, ODE discussed fiscal requirements for all Title I schools and relevant waivers under ESEA flexibility, including the availability of funds previously set-aside for professional development, supplemental educational services (SES), and choice related transportation for LEAs that do not have identified priority or focus schools. The SEA also indicated that it held conversations with LEA staff regarding the best uses of these “freed up funds.” The SEA also provided to ED evidence of the revisions it made to its consolidated application that accurately reflect these changes in set-asides required of LEAs. ODE conducted “Unwrapping School Improvement” workshops with representatives from all priority and focus schools August 13 and 16, 2012 in which it provided fiscal guidance to LEAs that explained that the 10 percent LEA professional development set aside ended in 2011–2012; SES and school choice and the requisite set-asides are no longer required; up to a 20 percent LEA level set aside may be required in 2013–2014 and 2014–2015 for LEAs with priority and focus schools, dependent upon needs identified in an LEA’s and school’s CAPs; priority and focus schools will continue to be required to set aside 10 percent for professional development activities; and non-SIG priority and focus schools will receive $5000 in initial planning grants from the SEA’s 1003(a) funds. |
| Next Steps | None. |

| Rank Order | The SEA ensures that its LEAs with Title I-eligible high schools with graduation rates below 60 percent that are identified as priority schools correctly implement the waiver that allows them to serve these schools out-of-rank order. |
| --- | --- |
| Summary of Progress | The SEA has not identified any Title I-eligible high schools with graduation rates below 60 percent as priority schools and, therefore, does not have any LEAs that are taking advantage of the waiver to serve these schools out-of-rank order based on poverty rate. |
| Next Steps | None. |